## Award Ceremony Checklist
Award Ceremony Planning Checklist
End-to-end award ceremony checklist — planning, judging, logistics, communications, event day, and post-event
S.No. | Phase | Task | Description | Responsible | Target Date | Done Date | Status | Cost (AED) | Notes
1 | Planning | Define awards categories | Determine award categories and eligibility criteria | Events Manager | 2026-01-01 | 2026-01-02 | Done | 0 | 8 categories confirmed
2 | Planning | Set budget and get approval | Prepare detailed budget — AED 120K approved | Events Manager | 2026-01-03 | 2026-01-05 | Done | 0
3 | Planning | Select venue | Book Grand Hyatt Ballroom — 200 pax | Events Manager | 2026-01-05 | 2026-01-08 | Done | 45000 | Deposit paid
4 | Planning | Fix date and send save-the-date | Ceremony date: 15 Mar 2026 — save the date sent | Events Manager | 2026-01-08 | 2026-01-10 | Done | 0 | 200 invites sent
5 | Planning | Appoint MC / Host | Engage professional MC for ceremony | Events Manager | 2026-01-10 | 2026-01-12 | Done | 5000 | Ahmed Al Nouri confirmed
6 | Planning | Launch nominations | Open nomination portal — 3-week window | Events Manager | 2026-01-12 | 2026-01-12 | Done | 0 | 185 nominations received
7 | Judging | Form judging panel | Appoint 5 independent judges per category | Events Manager | 2026-01-15 | 2026-01-18 | Done | 0 | 40 judges confirmed
8 | Judging | Share judging criteria | Brief judges on scoring methodology | Events Manager | 2026-01-20 | 2026-01-20 | Done | 0 | Scoring rubric shared
9 | Judging | Judging process | Panel reviews and scores all nominees | Judges | 2026-01-25 | 2026-01-30 | Done | 0 | Completed — results sealed
10 | Judging | Finalise winners | Tabulate scores — winners confirmed confidentially | Events Manager | 2026-02-01 | 2026-02-02 | Done | 0 | Under strict embargo
11 | Logistics | Design and print trophies | Custom trophies — crystal with engraving | Events Manager | 2026-02-05 | 2026-02-28 | Done | 18000 | 8 trophies — lead time 3 weeks
12 | Logistics | Design and print certificates | Personalised certificates for all winners | Marketing | 2026-02-05 | 2026-02-20 | Done | 3000
13 | Logistics | AV and stage setup | Stage design, LED backdrop, microphones, lighting | AV Company | 2026-03-01 | 2026-03-14 | Done | 15000 | Setup on 14 Mar
14 | Logistics | Arrange catering | 3-course dinner for 200 guests | Events Manager | 2026-02-01 | 2026-02-10 | Done | 35000 | Royal Feast Catering
15 | Logistics | Photographer and videographer | Full event coverage — photo and video | Events Manager | 2026-02-05 | 2026-02-10 | Done | 8000 | Lens & Light Studio
16 | Comms | Design event programme | Printed programme — agenda, nominees list | Marketing | 2026-03-01 | 2026-03-08 | Done | 4000 | 500 copies printed
17 | Comms | VIP and speaker briefing | Brief CEO, board, and presenters on script | Events Manager | 2026-03-10 |  | In Progress | 0 | Rehearsal on 13 Mar
18 | Event Day | Venue setup — morning of event | Oversee full venue setup by 14:00 | Events Manager | 2026-03-15 |  | Pending | 0 | Access from 09:00
19 | Event Day | Guest registration and welcome | Registration desk, name badges, seating guide | Events Team | 2026-03-15 |  | Pending | 0 | Doors open 18:30
20 | Post-Event | Thank you and media coverage | Send thank you to attendees, share media, press release | Marketing | 2026-03-18 |  | Pending | 0 | Within 48 hrs

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit