## Product Launch Planner
Product Launch Event Planner
Plan and track a product launch event — strategy, venue, product prep, marketing, logistics, event day, and post-launch follow-up
S.No. | Phase | Task | Description | Owner | Target Date | Done Date | Status | Budget (AED) | Actual (AED) | Notes
1 | Strategy | Define launch objectives | Set goals — awareness, leads, sales targets | Marketing Dir | 2026-01-01 | 2026-01-02 | Done | 0 | 0 | Target: 200 leads, 50 sales on day 1
2 | Strategy | Set launch date and format | Hybrid event — live + livestream | Marketing Dir | 2026-01-02 | 2026-01-03 | Done | 0 | 0 | Launch date: 15 Mar 2026
3 | Strategy | Define target audience | B2B clients, media, influencers, prospects | Marketing | 2026-01-03 | 2026-01-03 | Done | 0 | 0 | 300 in-person, 1000 online
4 | Strategy | Approve launch budget | Total budget AED 180,000 approved | CFO | 2026-01-05 | 2026-01-06 | Done | 0 | 0 | Board approved
5 | Venue | Book venue | Grand Hyatt Ballroom — 300 pax | Events Mgr | 2026-01-08 | 2026-01-10 | Done | 55000 | 55000 | Deposit paid
6 | Venue | Tech and AV setup | LED wall, stage, streaming setup, mics | AV Company | 2026-03-01 | 2026-03-14 | Done | 25000 | 24500 | Setup on 14 Mar
7 | Product | Finalise product demo | Live demo script and backup recording | Product Team | 2026-02-01 | 2026-02-20 | Done | 0 | 0 | Demo runs 8 minutes
8 | Product | Prepare product video | 90-second launch video — cinematic quality | Agency | 2026-02-01 | 2026-02-28 | Done | 15000 | 14800 | Video approved by CEO
9 | Product | Print product brochures | 500 full-colour brochures + digital version | Marketing | 2026-03-01 | 2026-03-08 | Done | 4000 | 3800 | Print Express delivery
10 | Marketing | Build launch landing page | Event registration + product info + countdown | Digital Team | 2026-01-10 | 2026-01-25 | Done | 5000 | 4800 | Live — 450 registrations
11 | Marketing | Email invitations — 3 waves | Save the date, invite, reminder emails | Marketing | 2026-01-15 | 2026-01-20 | Done | 0 | 0 | Sent to 5,000 contacts
12 | Marketing | LinkedIn and social campaign | Teaser posts, countdown, speaker reveals | Social Media | 2026-02-01 | 2026-02-01 | Done | 8000 | 7500 | Strong engagement — 15K reach
13 | Marketing | Press release and media outreach | Send to 20 UAE media contacts | PR Manager | 2026-03-01 | 2026-03-05 | Done | 3000 | 3000 | Gulf News and Khaleej Times confirmed
14 | Marketing | Influencer briefing | Brief 5 influencers for live coverage | Marketing | 2026-03-01 | 2026-03-08 | Done | 10000 | 10000 | 5 influencers confirmed
15 | Logistics | Catering — cocktail reception | Standing reception — 300 guests, 2 hours | Events Mgr | 2026-01-15 | 2026-01-20 | Done | 18000 | 18000 | Royal Feast Catering confirmed
16 | Logistics | Gift bags for attendees | Branded gift bags — 300 units | Marketing | 2026-02-01 | 2026-02-28 | Done | 9000 | 8700 | Premium branded items
17 | Logistics | Event staff and ushers | 10 event staff, 2 photographers, 1 videographer | Events Mgr | 2026-03-01 | 2026-03-05 | Done | 12000 | 11800 | Briefed on 14 Mar
18 | Event Day | Venue setup and rehearsal | Full rehearsal — CEO, speakers, demo team | Events Mgr | 2026-03-14 | 2026-03-14 | Done | 0 | 0 | Rehearsal successful
19 | Event Day | Product launch event — live | 300 guests, livestream, demo, CEO speech | Full Team | 2026-03-15 | 2026-03-15 | Done | 0 | 0 | Sold 68 units on day 1 — exceeded target
20 | Post-Launch | Lead follow-up and report | Follow up all leads — publish launch report | Sales + Mktg | 2026-03-18 |  | In Progress | 0 | 0 | 280 leads collected — follow-up in progress

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit