## Trade Show Planner
Trade Show & Exhibition Planner
Plan every trade show and exhibition task, owner, budget and deadline in one place.
S.No. | Task / Activity | Category | Owner | Vendor / Supplier | Due Date | Budget (AED) | Status | Priority | Remarks
1 | Book exhibition stand | Venue | Fatima H. | Expo Centre | 2026-02-10 | 12000 | Done | High | Hall 4 secured
2 | Stand design concept | Design | Rahul S. | Creative Hub | 2026-02-15 | 8500 | Done | High | Approved v2
3 | Stand fabrication | Build | Rahul S. | BuildPro | 2026-02-28 | 22000 | In Progress | High | 50% advance paid
4 | Print marketing collateral | Marketing | Aisha M. | PrintWorks | 2026-03-05 | 3200 | In Progress | Medium | Brochures and flyers
5 | Order branded giveaways | Marketing | Aisha M. | PromoGifts | 2026-03-08 | 2800 | Pending | Medium | Pens, bags, USBs
6 | Book staff travel | Logistics | Omar K. | SkyTravel | 2026-03-10 | 6500 | Pending | Medium | 4 staff flights
7 | Reserve hotel rooms | Logistics | Omar K. | City Hotel | 2026-03-10 | 5400 | Pending | Medium | 3 nights
8 | Arrange AV equipment | Tech | Rahul S. | AV Rentals | 2026-03-12 | 4100 | Pending | Low | Screens and speakers
9 | Prepare product demo | Content | Fatima H. | Internal | 2026-03-14 | 0 | In Progress | High | Demo script ready
10 | Schedule social posts | Marketing | Aisha M. | Internal | 2026-03-15 | 0 | Pending | Low | Teaser campaign
11 | Confirm internet line | Tech | Omar K. | Expo Centre | 2026-03-16 | 900 | Pending | Medium | Wired connection
12 | Brief booth staff | HR | Fatima H. | Internal | 2026-03-18 | 0 | Pending | Medium | Roster and roles
13 | Order catering | Logistics | Omar K. | FreshBite | 2026-03-18 | 3600 | Pending | Low | Daily refreshments
14 | Set up lead capture | Tech | Rahul S. | ScanLead | 2026-03-19 | 1500 | Pending | High | QR badge scanners
15 | Print name badges | Marketing | Aisha M. | PrintWorks | 2026-03-19 | 600 | Pending | Low | Staff and VIP
16 | Final stand walkthrough | Build | Rahul S. | BuildPro | 2026-03-20 | 0 | Pending | High | Snag list check
17 | Press and PR outreach | Marketing | Aisha M. | MediaLink | 2026-03-17 | 2200 | Pending | Medium | Invite key media
18 | Post-show follow-up plan | Sales | Fatima H. | Internal | 2026-03-25 | 0 | Pending | Medium | Lead nurture sequence

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit