## Party Planner
Birthday Party Planner
Plan and track all birthday party tasks, vendors, costs, and completion status in one organised sheet
S.No. | Task Category | Task / Item | Vendor / Contact | Estimated Cost (AED) | Actual Cost (AED) | Due Date | Completed | Notes
1 | Venue | Book party hall — 50 guests capacity | Grand Events Hall — 050-1234567 | 3000 | 3000 | 2026-02-01 | Yes | Deposit AED 500 paid
2 | Venue | Arrange table and chair layout | Grand Events Hall | 0 | 0 | 2026-03-10 | No | Included in venue package
3 | Catering | Birthday cake — 3 tier chocolate | Sweet Dreams Bakery - 055-9876543 | 800 | 800 | 2026-03-12 | Yes | Pickup on party day
4 | Catering | Snacks and finger food for 50 pax | Royal Feast Catering — 056-1122334 | 2500 | 0 | 2026-03-14 | No | Menu confirmed
5 | Catering | Soft drinks and juices | Al Meera Supermarket | 400 | 380 | 2026-03-14 | Yes
6 | Decoration | Balloon decoration — blue and gold theme | Balloon World UAE — 052-3344556 | 600 | 0 | 2026-03-14 | No | Setup on party day
7 | Decoration | Birthday banner and backdrop | Print Express — 054-5566778 | 250 | 250 | 2026-03-05 | Yes | Delivered
8 | Decoration | Table centrepieces and flowers | Bloom & Blossom — 052-9990001 | 400 | 0 | 2026-03-13 | No | Confirm design by 10 Mar
9 | Entertainment | DJ and sound system — 4 hours | SoundWave Events — 054-2223334 | 1500 | 0 | 2026-03-15 | No | Playlist to be shared
10 | Entertainment | Kids magic show — 1 hour | Magic Moments UAE — 050-7788990 | 800 | 800 | 2026-03-15 | Yes | Paid in full
11 | Entertainment | Photo booth rental — 3 hours | SnapBox UAE — 055-4455667 | 700 | 0 | 2026-03-15 | No | Props included
12 | Invitations | Design and print invitations — 60 cards | Print Express | 150 | 150 | 2026-03-01 | Yes | Distributed to guests
13 | Invitations | WhatsApp digital invitation | Self | 0 | 0 | 2026-02-28 | Yes | Sent to all contacts
14 | Gifts & Favours | Return gifts for guests — 50 units | Gift World UAE — 056-6677889 | 750 | 0 | 2026-03-13 | No | Personalised bags
15 | Gifts & Favours | Gift wrapping and ribbons | Al Meera Supermarket | 100 | 80 | 2026-03-13 | Yes
16 | Photography | Party photographer — 4 hours | Lens & Light Studio — 055-3334445 | 1200 | 600 | 2026-03-15 | No | 50% advance paid
17 | Logistics | Party day transport arrangement | Self | 200 | 0 | 2026-03-15 | No | Rent van for items
18 | Logistics | Setup and decoration team — 2 helpers | Self | 300 | 0 | 2026-03-15 | No | Friends helping
19 | Health & Safety | First aid kit | Self | 50 | 50 | 2026-03-14 | Yes
20 | Miscellaneous | Contingency budget |  | 500 | 0 | 2026-03-15 | No | Reserve for unexpected expenses

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit