## Baby Shower Budget
Baby Shower Budget Tracker
Plan and track all baby shower tasks, vendors, estimated and actual costs, bookings, and completion status
S.No. | Category | Task / Item | Vendor / Contact | Est. Cost (AED) | Actual Cost (AED) | Booking Date | Event Date | Status | Notes
1 | Venue | Home garden party — 25 guests | Home — our garden | 0 | 0 | 2026-01-15 | 2026-03-28 | Confirmed | Garden works perfectly
2 | Venue | Tent and seating rental | Event Rentals UAE | 1200 | 1200 | 2026-01-20 | 2026-03-28 | Confirmed | White tent + chairs + tables
3 | Decoration | Balloon arch — blue and gold | Balloon World UAE | 650 | 650 | 2026-02-01 | 2026-03-28 | Confirmed | 'It's a Boy' theme
4 | Decoration | Table centrepieces — 4 tables | Bloom & Blossom | 600 | 0 | 2026-02-15 | 2026-03-28 | Booked | Blue hydrangeas — beautiful
5 | Decoration | Welcome sign and banner | Print Express | 250 | 250 | 2026-02-01 | 2026-03-28 | Done | Printed and collected
6 | Decoration | Nappy cake — decoration piece | Baby Creations UAE | 380 | 380 | 2026-02-01 | 2026-03-28 | Ordered | Nappies + toys — centrepiece
7 | Food | Catering — finger food and sandwiches | Afternoon Tea UAE | 2000 | 2000 | 2026-01-15 | 2026-03-28 | Confirmed | AED 80pp x 25 guests
8 | Food | Cake — 2-tier baby shower cake | Sweet Dreams Bakery | 550 | 550 | 2026-02-01 | 2026-03-28 | Ordered | Blue and white — baby design
9 | Food | Cupcakes — 25 pcs baby themed | Sweet Dreams Bakery | 300 | 300 | 2026-02-01 | 2026-03-28 | Ordered | For each guest
10 | Food | Mocktail station — soft drinks bar | Self — prepare | 300 | 0 | 2026-03-27 | 2026-03-28 | Pending | Lemonade and fruit punch
11 | Invitations | Digital invites — WhatsApp | Canva — self designed | 0 | 0 | 2026-01-15 | 2026-03-01 | Done | Sent to 25 guests — RSVP 20
12 | Games | Baby shower games pack — 5 games | Party World UAE | 150 | 150 | 2026-02-01 | 2026-03-28 | Done | Guess the baby weight etc
13 | Games | Prize hampers for winners — 3 prizes | Gift World UAE | 450 | 450 | 2026-02-01 | 2026-03-28 | Done | 3 gift hampers ready
14 | Photography | Photographer — 2 hours | Lens & Light Studio | 1000 | 500 | 2026-02-01 | 2026-03-28 | Booked | 50% deposit paid
15 | Gifts | Gift for mum-to-be from group | All guests contributing | 0 | 0 | 2026-03-15 | 2026-03-28 | Collecting | Group collection in progress
16 | Gifts | Guest goody bags — 25 bags | Gift World UAE | 600 | 600 | 2026-02-15 | 2026-03-28 | Ordered | Sweet treats + candle
17 | Mum | Sash and crown for mum-to-be | Party World UAE | 120 | 120 | 2026-02-01 | 2026-03-28 | Done | 'Mum to Be' — gold sparkle
18 | Logistics | Chair covers and table linen | Event Rentals UAE | 350 | 350 | 2026-01-20 | 2026-03-28 | Confirmed | Included in tent package
19 | Logistics | Helium balloons — 50 balloons | Balloon World UAE | 200 | 200 | 2026-02-01 | 2026-03-28 | Ordered | Float around garden
20 | Misc | Contingency | Reserve | 400 | 0 |  | 2026-03-28 | Reserved | For last minute items

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit