## Home Projects
Home Improvement Project Tracker
Plan home improvement tasks by room, contractor, budget and status in one tracker.
S.No. | Project / Task | Room / Area | Contractor | Start Date | Target Date | Est. Cost (AED) | Status | Priority | Remarks
1 | Repaint walls | Living Room | BrightCoat | 2026-01-05 | 2026-01-09 | 1200 | Done | Medium | Two coats
2 | Replace tiles | Kitchen | TileWorks | 2026-01-10 | 2026-01-18 | 3500 | In Progress | High | Floor only
3 | Fix leaking tap | Bathroom | QuickFix | 2026-01-08 | 2026-01-08 | 150 | Done | High | Cartridge replaced
4 | Install shelves | Study | Self | 2026-01-12 | 2026-01-13 | 300 | Done | Low | Floating shelves
5 | Service AC units | All Rooms | CoolAir | 2026-01-15 | 2026-01-16 | 600 | Done | Medium | Annual service
6 | Replace door lock | Main Door | SecureHome | 2026-01-18 | 2026-01-19 | 450 | In Progress | High | Smart lock
7 | Garden landscaping | Backyard | GreenScape | 2026-01-20 | 2026-01-28 | 2800 | Planned | Low | Quote approved
8 | Waterproof terrace | Terrace | SealPro | 2026-01-22 | 2026-01-30 | 2200 | Planned | Medium | Before monsoon
9 | Upgrade lighting | Living Room | BrightCoat | 2026-01-25 | 2026-01-27 | 900 | Planned | Low | LED switch
10 | Repair wardrobe | Bedroom | WoodCraft | 2026-01-28 | 2026-01-31 | 700 | Planned | Medium | Hinge and rail
11 | Pest control | Whole House | SafeGuard | 2026-02-02 | 2026-02-02 | 350 | Done | High | Quarterly
12 | Replace geyser | Bathroom | QuickFix | 2026-02-04 | 2026-02-05 | 800 | In Progress | High | Old unit failed
13 | Paint ceiling | Bedroom | BrightCoat | 2026-02-06 | 2026-02-08 | 650 | Planned | Low | Damp patch
14 | Fix window seal | Study | SealPro | 2026-02-09 | 2026-02-10 | 250 | Planned | Medium | Draft issue
15 | Install curtains | Living Room | Self | 2026-02-11 | 2026-02-12 | 500 | Planned | Low | Blackout
16 | Deep clean sofa | Living Room | CleanCo | 2026-02-13 | 2026-02-13 | 300 | Done | Low | Steam clean
17 | Replace doorbell | Main Door | SecureHome | 2026-02-16 | 2026-02-16 | 180 | Planned | Low | Wireless
18 | Kitchen cabinet paint | Kitchen | WoodCraft | 2026-02-18 | 2026-02-22 | 1100 | Planned | Medium | Refinish

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit