## Receiving Log
Warehouse Receiving Log
Record all incoming goods receipts — quantities, conditions, storage locations, variances, and actions taken
S.No. | Received Date | GRN No. | PO Number | Supplier Name | Item Name | Qty Ordered | Qty Received | Unit | Condition | Storage Location | Received By | Variance | Action Taken | Status
1 | 2026-01-02 | GRN-001 | PO-2026-001 | Gulf Cement LLC | Portland Cement OPC 43 | 200 | 200 | Bags | Good | Store A-1 | Omar Qureshi | None | N/A | Accepted
2 | 2026-01-03 | GRN-002 | PO-2026-002 | Steel Arabia Co. | TMT Steel Bars 12mm | 10 | 10 | MT | Good | Yard B-2 | Hassan Ali | None | N/A | Accepted
3 | 2026-01-04 | GRN-003 | PO-2026-003 | Al Noor Aggregates | River Sand | 80 | 75 | m3 | Good | Yard A-1 | Omar Qureshi | 5 m3 short | Notified supplier | Partial — shortage
4 | 2026-01-05 | GRN-004 | PO-2026-004 | OfficeWorld | A4 Paper 80gsm | 50 | 50 | Ream | Good | Store C-3 | Divya Singh | None | N/A | Accepted
5 | 2026-01-06 | GRN-005 | PO-2026-005 | MedSupply Gulf | Paracetamol 500mg Tabs | 100 | 100 | Box | Good | Store D-1 | Hassan Ali | None | N/A | Accepted
6 | 2026-01-07 | GRN-006 | PO-2026-006 | PackagePro India | Cardboard Boxes Small | 500 | 480 | Pcs | Good | Store B-2 | Omar Qureshi | 20 short | Partial delivery noted | Partial — balance pending
7 | 2026-01-08 | GRN-007 | PO-2026-007 | CleanPro Services | Floor Cleaner 5L | 24 | 24 | Can | Good | Store C-1 | Divya Singh | None | N/A | Accepted
8 | 2026-01-09 | GRN-008 | PO-2026-008 | SafeGuard UAE | Safety Helmets | 30 | 30 | Pcs | Good | Store E-1 | Hassan Ali | None | N/A | Accepted
9 | 2026-01-10 | GRN-009 | PO-2026-009 | Electro Supplies | Extension Cords 3m | 20 | 18 | Pcs | Good | Store E-2 | Omar Qureshi | 2 short | Supplier informed | Partial — credit note
10 | 2026-01-11 | GRN-010 | PO-2026-010 | TechFix IT | Printer Toner Black | 5 | 5 | Cart | Good | Store C-4 | Divya Singh | None | N/A | Accepted
11 | 2026-01-12 | GRN-011 | PO-2026-011 | Gulf Maintenance | WD-40 Lubricant 400ml | 24 | 24 | Can | Good | Store F-1 | Hassan Ali | None | N/A | Accepted
12 | 2026-01-13 | GRN-012 | PO-2026-012 | Hygiene World UAE | Hand Sanitizer 500ml | 150 | 150 | Pcs | Good | Store D-2 | Omar Qureshi | None | N/A | Accepted
13 | 2026-01-14 | GRN-013 | PO-2026-013 | Steel Arabia Co. | Binding Wire | 100 | 100 | Kg | Good | Yard B-3 | Hassan Ali | None | N/A | Accepted
14 | 2026-01-15 | GRN-014 | PO-2026-014 | Tile Gallery LLC | Ceramic Floor Tiles | 400 | 350 | Box | Good | Store F-2 | Divya Singh | 50 short | Damaged in transit | Partial — insurance claim
15 | 2026-01-16 | GRN-015 | PO-2026-015 | Wood & More LLC | Plywood 18mm | 80 | 80 | Sheet | Good | Store B-4 | Omar Qureshi | None | N/A | Accepted
16 | 2026-01-17 | GRN-016 | PO-2026-016 | Chem Solutions UAE | Waterproofing Compound | 200 | 200 | Ltr | Good | Store G-1 | Hassan Ali | None | N/A | Accepted
17 | 2026-01-18 | GRN-017 | PO-2026-017 | PVC World Dubai | PVC Pipes 4 inch | 300 | 300 | Mtr | Good | Yard C-1 | Divya Singh | None | N/A | Accepted
18 | 2026-01-19 | GRN-018 | PO-2026-018 | Teak Craft LLC | Door Frames Teak | 20 | 15 | Nos | Good | Store B-5 | Omar Qureshi | 5 short | Balance ETA 25 Jan | Partial — balance pending
19 | 2026-01-20 | GRN-019 | PO-2026-019 | FireSafe LLC | Fire Extinguisher 4kg | 10 | 10 | Pcs | Good | Store E-3 | Hassan Ali | None | N/A | Accepted
20 | 2026-01-21 | GRN-020 | PO-2026-020 | Brick Masters LLC | Red Clay Bricks | 15000 | 14000 | Nos | Good | Yard A-2 | Divya Singh | 1000 short | Supplier to deliver | Partial — balance pending

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit