## Import Tracker
Import Shipment Tracker
Track all import shipments — supplier, origin, costs, freight, customs duty, ETD, ETA, customs clearance, and delivery status
S.No. | Shipment Ref | Supplier | Origin | Items | PO Number | Qty | Unit | Invoice (AED) | Freight (AED) | Duty (AED) | Total Cost | Mode | ETD | ETA | Arrived | Cleared | Status | Notes
1 | SHP-2026-001 | Steel Arabia Co. | Saudi Arabia | TMT Steel Bars 12mm — 50 MT | PO-2026-002 | 50 | MT | 190000 | 8500 | 0 | 198500 | Land Truck | 2026-01-02 | 2026-01-05 | 2026-01-05 | Yes | Delivered | GCC — no duty
2 | SHP-2026-002 | PackagePro India | India | Cardboard Boxes — 2000 pcs | PO-2026-006 | 2000 | Pcs | 7000 | 2200 | 875 | 10075 | Sea FCL | 2026-01-05 | 2026-01-20 | 2026-01-21 | Yes | Delivered | 1 day delay — port congestion
3 | SHP-2026-003 | MedSupply Gulf | Jordan | Medical Supplies Lot | PO-2026-005 | 1 | Lot | 18000 | 1200 | 0 | 19200 | Air | 2026-01-08 | 2026-01-10 | 2026-01-10 | Yes | Delivered | Air — urgent pharma
4 | SHP-2026-004 | Chem Solutions | Germany | Waterproofing Compound 500L | PO-2026-018 | 500 | Ltr | 42500 | 3800 | 5100 | 51400 | Sea LCL | 2026-01-10 | 2026-01-28 |  | No | In Transit | ETA 28 Jan — on track
5 | SHP-2026-005 | Teak Craft LLC | Indonesia | Teak Door Frames — 50 sets | PO-2026-016 | 50 | Sets | 35000 | 4200 | 4375 | 43575 | Sea FCL | 2026-01-12 | 2026-02-02 |  | No | In Transit
6 | SHP-2026-006 | Wood More LLC | Malaysia | Plywood 18mm — 200 sheets | PO-2026-015 | 200 | Sheets | 14000 | 2800 | 1750 | 18550 | Sea LCL | 2026-01-15 | 2026-02-05 |  | No | In Transit | Consolidated shipment
7 | SHP-2026-007 | Tile Gallery LLC | Italy | Ceramic Floor Tiles — 500 boxes | PO-2026-009 | 500 | Boxes | 110000 | 9500 | 13750 | 133250 | Sea FCL | 2026-01-15 | 2026-02-10 |  | No | In Transit | High value — insured
8 | SHP-2026-008 | Kitchen World UAE | Germany | Kitchen Cabinetry — 5 units | PO-2026-017 | 5 | Sets | 600000 | 22000 | 75000 | 697000 | Sea FCL | 2026-01-18 | 2026-02-15 |  | No | In Transit | Custom heavy duty order
9 | SHP-2026-009 | Glass Tech UAE | China | Toughened Glass 6mm — 1000sqft | PO-2026-019 | 1000 | Sqft | 95000 | 7500 | 11875 | 114375 | Sea FCL | 2026-01-20 | 2026-02-18 |  | No | In Transit | Fragile — handle with care
10 | SHP-2026-010 | Electro Supplies | China | Electrical Cables and Fittings | PO-2026-021 | 1 | Lot | 35000 | 4500 | 4375 | 43875 | Sea LCL | 2026-01-22 | 2026-02-20 |  | No | Booked | Booking confirmed
11 | SHP-2026-011 | OfficeWorld | UAE | Office Stationery Lot | PO-2026-004 | 1 | Lot | 4500 | 0 | 0 | 4500 | Local | 2026-01-25 | 2026-01-26 | 2026-01-26 | Yes | Delivered | Local supplier
12 | SHP-2026-012 | SafeGuard UAE | UAE | Safety Equipment PPE Lot | PO-2026-022 | 1 | Lot | 12000 | 0 | 0 | 12000 | Local | 2026-01-25 | 2026-01-26 | 2026-01-27 | Yes | Delivered | 1 day delay
13 | SHP-2026-013 | Brick Masters LLC | Oman | Red Clay Bricks — 30,000 | PO-2026-023 | 30000 | Nos | 42000 | 3200 | 0 | 45200 | Land Truck | 2026-01-27 | 2026-01-30 |  | No | In Transit | GCC — no duty
14 | SHP-2026-014 | PVC World Dubai | UAE | PVC Pipes and Fittings | PO-2026-024 | 1 | Lot | 18000 | 0 | 0 | 18000 | Local | 2026-01-28 | 2026-01-29 |  | No | Scheduled
15 | SHP-2026-015 | Gulf Cement LLC | UAE | Portland Cement — 500 bags | PO-2026-025 | 500 | Bags | 16250 | 500 | 0 | 16750 | Local | 2026-01-29 | 2026-01-30 |  | No | Scheduled | Local — no freight issue
16 | SHP-2026-016 | Form Work UAE | UAE | Aluminium Shuttering 2000sqft | PO-2026-026 | 2000 | Sqft | 66000 | 800 | 0 | 66800 | Local | 2026-01-30 | 2026-01-31 |  | No | Scheduled
17 | SHP-2026-017 | ColourMax UAE | India | Paint and Primer — 500 litres | PO-2026-027 | 500 | Ltr | 32500 | 3200 | 4063 | 39763 | Sea LCL | 2026-02-01 | 2026-02-20 |  | No | Planned
18 | SHP-2026-018 | WaterPro UAE | UAE | Waterproofing Membrane 1000sqm | PO-2026-028 | 1000 | Sqm | 45000 | 0 | 0 | 45000 | Local | 2026-02-02 | 2026-02-03 |  | No | Planned
19 | SHP-2026-019 | Bitumen Gulf LLC | Bahrain | Bitumen Waterproofing 500kg | PO-2026-029 | 500 | Kg | 18000 | 1800 | 0 | 19800 | Land Truck | 2026-02-03 | 2026-02-05 |  | No | Planned | GCC — no duty
20 | SHP-2026-020 | Smart Tech | USA | Automation Control System | PO-2026-030 | 1 | Unit | 85000 | 6500 | 10625 | 102125 | Air | 2026-02-05 | 2026-02-08 |  | No | Planned | Urgent — air freight

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit