## Benefits Tracker
Project Benefits Tracker
Track realisation of project benefits post-implementation — KPIs, baseline, targets, actual values, and benefit owner
S.No. | Benefit Category | Benefit Description | KPI | Baseline Value | Target Value | Measurement Date | Actual Value | Benefits Realised % | Benefit Owner | Status | Remarks
1 | Financial | Reduce processing costs by 25% | Processing cost AED/month | AED 80K | AED 60K | 2026-06-30 | AED 68K | 60% | CFO | On Track | Q2 review due
2 | Financial | Increase revenue from new channel | Monthly revenue AED | AED 0 | AED 500K | 2026-12-31 | AED 180K | 36% | Sales Dir | In Progress | Growing monthly
3 | Financial | Reduce manual effort — save 200 hrs/mo | Hours saved per month | 0 hrs | 200 hrs | 2026-06-30 | 140 hrs | 70% | COO | On Track
4 | Operational | Improve delivery accuracy to 99% | Delivery accuracy % | 92% | 99% | 2026-12-31 | 96% | 57% | Ops Manager | In Progress | Steady improvement
5 | Operational | Reduce error rate by 80% | Error rate per 1000 txns | 45 | 9 | 2026-06-30 | 18 | 75% | QC Manager | On Track
6 | Operational | Cut process cycle time from 5 to 2 days | Average cycle time days | 5 days | 2 days | 2026-12-31 | 3.5 days | 50% | COO | In Progress | Automation helping
7 | Customer | Improve NPS score from 42 to 65 | NPS Score | 42 | 65 | 2026-12-31 | 54 | 52% | CCO | In Progress | Quarterly survey done
8 | Customer | Reduce complaint resolution time | Avg resolution hours | 48 hrs | 8 hrs | 2026-06-30 | 18 hrs | 75% | CS Head | On Track
9 | Customer | Increase customer retention to 92% | Retention rate % | 82% | 92% | 2026-12-31 | 87% | 50% | CCO | In Progress
10 | People | Reduce staff overtime by 40% | Overtime hours/month | 320 hrs | 192 hrs | 2026-06-30 | 240 hrs | 67% | HR Manager | On Track | Automation reducing OT
11 | People | Improve staff satisfaction score | eNPS score | 35 | 55 | 2026-12-31 | 44 | 47% | HR Manager | In Progress | Engagement survey Q2
12 | People | Upskill 80% of team on new system | Training completion % | 0% | 80% | 2026-06-30 | 65% | 81% | L&D Lead | On Track
13 | Strategic | Enter 2 new market segments | New segments launched | 0 | 2 | 2026-12-31 | 1 | 50% | CEO | In Progress | 1 more planned Q3
14 | Strategic | Achieve ISO 27001 certification | Cert obtained Yes/No | No | Yes | 2026-09-30 | In Progress | 40% | IT Manager | In Progress | Gap assessment done
15 | Strategic | Launch 3 new product features | Features launched | 0 | 3 | 2026-12-31 | 1 | 33% | Product Mgr | In Progress | 2 in development
16 | Compliance | Achieve 100% regulatory compliance | Compliance audit score | 78% | 100% | 2026-06-30 | 92% | 70% | Compliance | On Track | 3 minor gaps remain
17 | Technology | Reduce system downtime to <0.1% | Monthly downtime % | 1.2% | 0.1% | 2026-12-31 | 0.4% | 73% | IT Manager | On Track
18 | Technology | Automate 5 manual reporting processes | Processes automated | 0 | 5 | 2026-12-31 | 3 | 60% | IT Manager | In Progress | 2 more in backlog
19 | Environmental | Reduce paper usage by 60% | Monthly paper reams used | 80 | 32 | 2026-06-30 | 48 | 67% | Admin Mgr | On Track | Digital forms live
20 | Environmental | Reduce energy consumption by 15% | Monthly kWh usage | 12500 | 10625 | 2026-12-31 | 11800 | 41% | Facilities | In Progress | LED upgrade in Q3

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit