## Handover Report
Project Handover Report
Structured project handover report — deliverables, open items, support transition, lessons learned, and formal sign-offs
S.No. | Section | Item | Details | Status | Owner | Handover Date | Accepted By | Notes
1 | Project Summary | Project name and scope | ERP Implementation — Finance and HR Modules | Complete | PM | 2026-01-31 | Sponsor | Final scope delivered as agreed
2 | Project Summary | Total budget and actual spend | Budget AED 2.5M — Actual AED 2.42M — 3.2% under | Complete | CFO | 2026-01-31 | Finance Dir | Under budget — AED 80K saving
3 | Project Summary | Timeline — planned vs actual | Planned 12 months — Actual 12.5 months — 2 week delay | Complete | PM | 2026-01-31 | Sponsor | Delay due to UAT extension
4 | Deliverables | System go-live confirmation | ERP live in production since 15 Jan 2026 | Complete | Tech Lead | 2026-01-31 | CTO | 99.9% uptime post go-live
5 | Deliverables | User training completion | 420 users trained — 98% completion rate | Complete | L&D Lead | 2026-01-31 | HR Director | Training materials in SharePoint
6 | Deliverables | Documentation package | User manuals, SOPs, and admin guides delivered | Complete | BA | 2026-01-31 | Operations | All docs on SharePoint — IT folder
7 | Deliverables | Data migration sign-off | 100% of data migrated — zero loss confirmed | Complete | Data Lead | 2026-01-31 | CTO | Migration validation report attached
8 | Deliverables | Integration testing sign-off | All 8 integrations tested and live | Complete | Tech Lead | 2026-01-31 | CTO
9 | Open Items | Outstanding defects | 3 minor defects open — P3 priority | In Progress | Dev Team | 2026-02-28 | CTO | Target closure by 28 Feb
10 | Open Items | Advanced user training | Power user training for 15 super users pending | Pending | L&D Lead | 2026-02-28 | HR Director | Scheduled 5 Feb
11 | Open Items | Legacy system decommission | Old system to be switched off by end Feb | Pending | IT Manager | 2026-02-28 | CTO | Data archiving in progress
12 | Support Handover | Support team briefed | IT helpdesk trained on new system — L1 support live | Complete | IT Manager | 2026-01-31 | CTO
13 | Support Handover | Hypercare period | Hypercare support active until 28 Feb 2026 | Active | Dev Team | 2026-02-28 | CTO | Daily stand-up during hypercare
14 | Support Handover | Vendor support contract | SAP support contract active — AED 180K/yr | Active | Procurement | 2026-01-31 | CFO | Contract ref: SAP-2026-001
15 | Lessons Learned | What went well | Strong exec sponsorship, good team collaboration | Noted | PM | 2026-01-31 | Sponsor | Document for future projects
16 | Lessons Learned | What could improve | UAT planning needs more time — allow 6 weeks | Noted | PM | 2026-01-31 | Sponsor | Add to project methodology
17 | Lessons Learned | Key risks that materialised | Data quality issues — extra cleansing sprint needed | Noted | PM | 2026-01-31 | Sponsor
18 | Sign-offs | Sponsor sign-off | Project closure approved by CEO — Mr. Ahmed Al Nouri | Complete | Sponsor | 2026-01-31 | CEO | Signed 31 Jan 2026
19 | Sign-offs | Business owner acceptance | Finance and HR directors accepted deliverables | Complete | Business Owner | 2026-01-31 | Finance + HR | Acceptance signed
20 | Sign-offs | IT acceptance | CTO signed off technical deliverables | Complete | CTO | 2026-01-31 | CTO | Technical closure confirmed

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit