## PIR
Post-Implementation Review
Evaluate completed project across delivery, quality, stakeholders, team, and benefits — capturing lessons learned and actions for future projects
S.No. | Review Area | Review Question | Response / Finding | Rating (1-5) | What Went Well | What to Improve | Lesson Learned | Owner | Priority | Action for Next Project
1 | Project Delivery | Was the project delivered on time? | Delivered 2 weeks late due to UAT extension | 3 | Strong planning in early phases | Allow more time for UAT | UAT needs minimum 5 weeks for this scale | PM | High | Add buffer to UAT phase in future
2 | Project Delivery | Was the project delivered within budget? | AED 2.42M vs AED 2.5M budget — under budget | 5 | Strong cost control throughout | None — under budget | Reserve contingency but monitor tightly | CFO | Low | Maintain current cost control approach
3 | Project Delivery | Was scope delivered in full? | 98% of scope delivered — 1 feature deferred | 4 | Good scope management — CRs controlled | Deferred feature should be tracked | Track deferred scope in benefits register | PM | Medium | Add deferred scope tracker to closure docs
4 | Quality | Was the solution quality acceptable? | Post go-live defects higher than expected | 3 | Core functionality solid | More thorough regression testing needed | Automated regression testing saves time | QA Lead | High | Implement automated regression suite
5 | Quality | Was documentation complete and useful? | 80% of docs complete — user guides lacking | 3 | Technical docs excellent | User guides need more screenshots | User guides should be co-created with users | BA | Medium | Involve end users in guide creation
6 | Stakeholder | Was stakeholder engagement effective? | Good at exec level — weaker at user level | 3 | Executive sponsorship was strong | Need more mid-level manager engagement | Middle management is key change agent | Change Mgr | High | Include mid-managers in steering
7 | Stakeholder | Was communication effective? | Weekly updates well received by most | Yes | Regular email updates appreciated | Some stakeholders wanted more detail | Tailor comms by stakeholder group | PM | Medium | Segment comms by audience type
8 | Team | Did the project team work well? | Team cohesion was strong — good morale | 5 | Great team spirit — low conflict | None identified | Invest in team building early | PM | Low | Continue team events on future projects
9 | Team | Were skills and resources adequate? | Resource gap in data architecture | 3 | Strong dev and QA resources | Data architect needed earlier | Identify specialist roles in planning | PM | High | Include data architect in resource plan
10 | Vendor | Did vendors perform adequately? | Main vendor delivered — 3rd party API issues | 3 | Main vendor — excellent support | API vendor SLA needs tightening | SLA penalties for API downtime critical | Procurement | High | Tighten API vendor SLAs in future
11 | Risk Management | Were risks managed effectively? | 14 of 16 risks mitigated well | 4 | Risk workshops were very valuable | 2 risks escalated late | Escalate risks earlier — lower threshold | PM | Medium | Lower escalation threshold for risks
12 | Change Management | Was change managed well? | User adoption at 75% — target was 85% | 3 | Change champion network worked | More hands-on support needed at go-live | Hypercare period must be longer | Change Mgr | High | Extend hypercare to 6 weeks
13 | Benefits | Are benefits being realised? | Early signs positive — full review in 6 months | 3 | Cost savings tracking well | Revenue benefits need more time | Benefits take 6-12 months to materialise | Sponsor | Medium | Set 6-month and 12-month benefit reviews
14 | Process | Were project processes followed? | 80% adherence to PMO methodology | 4 | Change control was rigorous | Status reports occasionally late | Automate status report reminders | PMO | Low | Set up automated report reminders
15 | Technology | Was the technology the right choice? | Yes — ERP choice was correct | 5 | ERP performance exceeded expectations | API integration was underestimated | API complexity needs specialist assessment | Tech Lead | Medium | Add API assessment to tech selection
16 | Training | Was training effective? | Training well received but too short | 3 | Content quality was excellent | More practice time needed | Training needs hands-on lab sessions | L&D Lead | High | Build lab environment for training
17 | Testing | Was testing adequate? | UAT was thorough — SIT could improve | 3 | UAT sign-off process was rigorous | SIT lacked test automation | Automate SIT regression tests | QA Lead | High | Budget for test automation tools
18 | Governance | Was project governance strong? | Monthly steering effective | Yes | Steering committee well engaged | Project board quorum issue once | Quorum rules must be enforced | Company Sec | Low | Add quorum rule to project governance
19 | Lessons | What was the single biggest lesson? | Data quality must be assessed and fixed before migration | 5 | Data migration itself was smooth | Data quality was underestimated | Always run data quality sprint first | Data Lead | Critical | Mandate data quality sprint in all future projects
20 | Overall | Overall project success rating | Project rated 4.1 out of 5 by stakeholders | 4 | Strong delivery despite challenges | UAT and data planning need improvement | Document and share lessons across PMO | PM | High | Share lessons in PMO knowledge base

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit