## Benefits Tracker
Benefits Realisation Tracker
Track all project benefits against baseline and targets — 6-month, 12-month, and 18-month reviews with realisation percentage and status
S.No. | Benefit Name | Category | Description | Baseline Value | Target Value | Unit | Measurement Method | Owner | Planned Date | 6M Review | 12M Review | 18M Review | Realised % | Status | Notes
1 | Reduced manual reporting time | Efficiency | Automated reports replace manual Excel builds | 12 hrs/week | 2 hrs/week | Hrs | Time-tracking tool | Finance Dir | 2026-07-01 | 8 hrs | 4 hrs | 2 hrs | 75% | On Track | Automation 60% complete
2 | Faster month-end close | Efficiency | Month-end close from 8 days to 3 days | 8 days | 3 days | Days | Finance close calendar | CFO | 2026-07-01 | 7 days | 5 days | 3 days | 40% | On Track | ERP go-live driving this
3 | Reduced headcount cost — 2 FTEs | Financial | Automation removes 2 data entry roles | AED 240K/yr | AED 0 | AED | Payroll comparison | HR Director | 2027-01-01 | N/A | N/A | AED 240K | 0% | Pending | Roles not redeployed yet
4 | Improved data accuracy | Quality | Error rate in reports drops from 8% to 0.5% | 8% | 0.5% | % | Monthly audit sample | QA Manager | 2026-07-01 | 5% | 2% | 0.5% | 72% | On Track | UAT defects being fixed
5 | Customer satisfaction improvement | Customer | NPS improves from 42 to 65 post-transformation | 42 | 65 | NPS | Quarterly NPS survey | CCO | 2026-10-01 | N/A | 48 | 58 | 25% | On Track | Customer portal driving this
6 | Reduced IT support tickets | Efficiency | New system reduces helpdesk tickets by 40% | 350/month | 210/month | Tickets | Helpdesk system report | CTO | 2026-07-01 | 320 | 270 | 210 | 35% | On Track | Training reducing calls
7 | Revenue growth from new CRM | Financial | Better pipeline visibility adds AED 2M revenue | AED 8M | AED 10M | AED | Sales revenue report | Sales Dir | 2027-01-01 | N/A | AED 8.5M | AED 10M | 25% | On Track | CRM 3 months live
8 | Improved employee productivity | People | Staff save 3 hrs/week on admin tasks | 0 hrs saved | 3 hrs/week | Hrs | Productivity survey | HR Director | 2026-07-01 | 1 hr | 2 hrs | 3 hrs | 55% | On Track | Survey results positive
9 | Compliance audit pass rate | Compliance | Audit findings reduce from 18 to 3 per year | 18 findings | 3 findings | Nos | Internal audit report | Compliance | 2026-06-30 | 12 | 7 | 3 | 50% | On Track | PDPL compliance improving
10 | Vendor payment cycle reduction | Efficiency | AP payment cycle from 45 days to 20 days | 45 days | 20 days | Days | AP aging report | Finance Dir | 2026-07-01 | 38 | 28 | 20 | 28% | On Track | Automation of AP started
11 | Reduced paper usage — 80% | ESG | Paperless AP and HR processes | 5000 sheets | 1000 sheets | Sheets | Stationery order tracking | Sustainability | 2026-07-01 | 4000 | 2500 | 1000 | 25% | On Track | E-signature deployed
12 | Staff turnover reduction | People | Turnover drops from 18% to 10% through engagement | 18% | 10% | % | HR attrition report | HR Director | 2027-01-01 | N/A | 15% | 10% | 0% | Pending | Engagement programme live
13 | Improved forecast accuracy | Financial | Forecast vs actual variance below 5% | 18% var | 5% var | % | Monthly FP&A report | CFO | 2026-10-01 | N/A | 12% | 7% | 25% | On Track | FP&A tool being deployed
14 | Faster new hire onboarding | Efficiency | Onboarding time drops from 4 weeks to 2 weeks | 4 weeks | 2 weeks | Weeks | HR onboarding tracker | HR Director | 2026-07-01 | 4 wks | 3 wks | 2 wks | 0% | Pending | New HR system not live
15 | Reduced procurement cost — 12% | Financial | Better vendor mgmt saves 12% on procurement | AED 5M | AED 4.4M | AED | Procurement spend report | COO | 2027-01-01 | N/A | N/A | AED 4.4M | 0% | Pending | Vendor contracts up in Dec
16 | Real-time management dashboard | Visibility | CEO and HODs have live dashboards — no lag | 2 day lag | Real-time | Hrs | Dashboard uptime report | CTO | 2026-07-01 | 24hr | 4hr | Real-time | 50% | On Track | BI tool 70% deployed
17 | Improved supply chain visibility | Efficiency | End-to-end supply chain tracking live | 0% | 100% | % | SCM system dashboard | COO | 2026-10-01 | N/A | 40% | 100% | 0% | Planned | SCM module Q3
18 | Reduced system downtime | Technology | Downtime from avg 4 hrs/month to under 30 min | 4 hrs | 30 min | Hrs | IT incident log | CTO | 2026-07-01 | 3 hrs | 1.5 hrs | 30 min | 30% | On Track | Cloud migration helping
19 | Better customer data quality | Quality | Duplicate records in CRM from 22% to under 2% | 22% | 2% | % | CRM data quality report | Sales Dir | 2026-07-01 | 18% | 8% | 2% | 18% | On Track | Dedup tool deployed
20 | Increased cross-sell revenue | Financial | Cross-sell revenue grows AED 500K from CRM insights | AED 0 | AED 500K | AED | Sales product report | Sales Dir | 2027-01-01 | N/A | AED 80K | AED 500K | 16% | On Track | CRM driving opportunities

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit