## Meeting Minutes
Meeting Minutes – Project
Record agenda, discussions, decisions and action items for all project meetings
# | Agenda Item | Discussion Summary | Decision Taken | Action Item | Owner | Due Date | Status
1 | Project Status Update | Team reviewed progress against plan. Week 12 tasks are 80% complete. | Continue current pace; escalate blockers by EOD Friday | Update project tracker with latest % complete | All Team Leads | 20-Jun-25 | Open
2 | Budget Review | Finance confirmed spend is at 62% of approved budget. No overrun risk. | Proceed without budget revision | Share updated budget snapshot with sponsor | Finance Manager | 21-Jun-25 | Open
3 | Risk Discussion – Vendor Delay | Vendor ABC flagged a 2-week delay in material delivery. | Source alternative vendor for critical materials | Get 3 quotes from alternate vendors | Procurement Lead | 19-Jun-25 | In Progress
4 | Scope Change Request #4 | Client requested addition of reporting module. | Defer to Phase 2 to protect current timeline | Document SCR #4 as deferred; inform client formally | Project Manager | 20-Jun-25 | Open
5 | UAT Planning | UAT to begin Week 14. Test scripts 90% ready. | UAT kick-off confirmed for 30-Jun-25 | Finalise UAT test scripts and share with QA team | QA Lead | 23-Jun-25 | Open
6 | Resource Availability | Developer X on leave Week 13. Cover plan needed. | Assign Developer Y as backup for Week 13 | Update resource calendar | PM / HR | 18-Jun-25 | Completed
7 | Stakeholder Communication | Sponsor requested bi-weekly written status updates. | Agree to bi-weekly email update from PM | Draft template for bi-weekly status email | Project Manager | 22-Jun-25 | Open
8 | AOB | Team requested team lunch upon project completion. | PM to organise team recognition event at closure | Book venue for team event – budget AED 1,500 | PM / Admin | 30-Jun-25 | Planned

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit