## Action Register
Project Action Register
Track all project actions — owners, priorities, due dates, completion status, and impact if delayed
S.No. | Date Raised | Action Title | Description | Raised By | Assigned To | Priority | Due Date | Completed Date | Status | Impact if Delayed | Remarks
1 | 2026-01-02 | Sign off Project Charter | Get CEO signature on project charter | PM | CEO | High | 2026-01-05 | 2026-01-05 | Done | Blocks project kickoff | Signed on time
2 | 2026-01-02 | Confirm Project Team | Finalise all team members and roles | PM | HR Manager | High | 2026-01-05 | 2026-01-06 | Done | Delays all workstreams | Team confirmed
3 | 2026-01-03 | Setup Project SharePoint | Create project folder and share access | PM | IT Lead | Medium | 2026-01-07 | 2026-01-07 | Done | Collaboration impacted
4 | 2026-01-03 | Finalise Project Budget | Get finance sign-off on approved budget | PM | CFO | High | 2026-01-08 | 2026-01-09 | Done | Cannot procure resources | AED 2.5M approved
5 | 2026-01-05 | Kick off Meeting with Vendor | Schedule and conduct vendor kickoff call | PM | Procurement | High | 2026-01-10 | 2026-01-10 | Done | Vendor work delayed
6 | 2026-01-05 | Develop Project Schedule | Build detailed WBS and Gantt chart | PM | PM | High | 2026-01-12 | 2026-01-13 | Done | No baseline to track | Approved by sponsor
7 | 2026-01-08 | Complete Requirements Workshop | Facilitate full requirements session | BA | BA + Stakeholders | High | 2026-01-15 | 2026-01-15 | Done | Scope unclear | 12 attendees
8 | 2026-01-08 | Procure Development Licenses | Purchase required software licenses | Tech Lead | IT Manager | Medium | 2026-01-15 | 2026-01-16 | Done | Dev team blocked | 3 licenses purchased
9 | 2026-01-10 | Submit Design Mockups | Deliver UI/UX mockups for review | Designer | UX Designer | Medium | 2026-01-20 |  | In Progress | UAT delayed | 60% complete
10 | 2026-01-10 | Conduct Risk Workshop | Identify and rate all project risks | PM | Full Team | High | 2026-01-18 | 2026-01-18 | Done | Risks unmanaged | 14 risks identified
11 | 2026-01-12 | Setup Test Environment | Configure QA testing environment | Tech Lead | DevOps | High | 2026-01-20 |  | In Progress | Testing cannot start | ETA 22 Jan
12 | 2026-01-12 | Confirm UAT Participants | Identify business users for UAT | BA | Business Owner | Medium | 2026-01-20 |  | Pending | UAT resourcing gap | Awaiting names
13 | 2026-01-15 | Complete Data Migration Plan | Document data migration approach | Tech Lead | Data Architect | High | 2026-01-25 |  | In Progress | Go-live risk | Draft in review
14 | 2026-01-15 | Stakeholder Communication | Send project status update to all stakeholders | PM | PM | Medium | 2026-01-20 | 2026-01-20 | Done | Stakeholder misalignment | Monthly cadence set
15 | 2026-01-18 | Finalise Training Plan | Develop end-user training approach | BA | L&D Team | Medium | 2026-01-28 |  | Pending | Users unprepared for go-live
16 | 2026-01-18 | Resolve Integration Issue | Fix API integration between systems | Tech Lead | Dev Team | High | 2026-01-22 |  | In Progress | Data flow blocked | Root cause found
17 | 2026-01-20 | Get Legal Sign-off on Contract | Legal review of vendor contract | PM | Legal Counsel | High | 2026-01-25 |  | Pending | Vendor work on hold | Under review
18 | 2026-01-20 | Prepare Go-Live Checklist | Document all pre-go-live checks | PM | PM + Tech Lead | High | 2026-01-28 |  | Pending | Uncontrolled go-live
19 | 2026-01-22 | Update RAID Log | Refresh risks, actions, issues, decisions | PM | PM | Medium | 2026-01-25 |  | Pending | Governance gap | Weekly update needed
20 | 2026-01-25 | Submit Monthly Status Report | Prepare and send project status report | PM | PM | Medium | 2026-01-31 |  | Pending | Sponsor visibility lost | Due last day of month

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit