## Issue Priority Matrix
Issue Priority Matrix
Log and prioritise all project issues by impact and urgency — priority score, assignment, resolution, and status tracking
S.No. | Issue ID | Date Raised | Issue Title | Category | Impact (1-5) | Urgency (1-5) | Priority Score | Priority Level | Assigned To | Target Date | Resolved Date | Resolution | Status | Notes
1 | ISS-001 | 2026-01-02 | Production server down — site offline | Infrastructure | 5 | 5 | 25 | Critical | Hassan Ali | 2026-01-02 | 2026-01-02 | Server restarted — disk space cleared | Resolved | Resolved in 45 min
2 | ISS-002 | 2026-01-02 | Payment gateway rejecting transactions | Finance/Tech | 5 | 5 | 25 | Critical | CTO + Finance | 2026-01-02 | 2026-01-03 | API key expired — renewed | Resolved | Revenue impact AED 12K
3 | ISS-003 | 2026-01-03 | Data breach — customer email list exposed | Security | 5 | 4 | 20 | High | IT Security | 2026-01-03 | 2026-01-05 | Breach contained — DPA notified | Resolved | PDPL notification filed
4 | ISS-004 | 2026-01-03 | Key developer resigned — project at risk | Resources | 4 | 4 | 16 | High | PM + HR | 2026-01-10 |  | Contractor engaged as backup | In Progress | Contractor starts 10 Jan
5 | ISS-005 | 2026-01-04 | Client threatening contract termination | Commercial | 4 | 4 | 16 | High | Sara Al Noor | 2026-01-05 | 2026-01-05 | Exec call held — issue resolved | Resolved | Client retained
6 | ISS-006 | 2026-01-04 | Budget overrun — 15% above plan | Finance | 4 | 3 | 12 | High | CFO | 2026-01-15 |  | Reviewing discretionary spend | In Progress | Cost review in progress
7 | ISS-007 | 2026-01-05 | UAT failing — critical business processes | Quality | 4 | 3 | 12 | High | QA Lead | 2026-01-12 |  | Root cause identified — fix in progress | In Progress | 3 critical defects open
8 | ISS-008 | 2026-01-05 | Vendor delivered 3 weeks late | Vendor | 3 | 4 | 12 | High | Procurement | 2026-01-08 | 2026-01-08 | Penalty clause invoked — AED 25K claimed | Resolved | Claim submitted
9 | ISS-009 | 2026-01-06 | Regulatory compliance gap found in audit | Compliance | 4 | 3 | 12 | High | Legal Counsel | 2026-01-20 |  | Gap remediation plan in progress | In Progress | PDPL gap — action plan live
10 | ISS-010 | 2026-01-06 | Integration failing between CRM and ERP | Technology | 3 | 3 | 9 | Medium | Tech Lead | 2026-01-15 |  | API mapping issue — fix scheduled | In Progress | ETA 15 Jan
11 | ISS-011 | 2026-01-07 | Team morale low — 2 resignations this month | People | 3 | 3 | 9 | Medium | HR Director | 2026-01-20 |  | Exit interviews done — action plan created | In Progress | Engagement survey planned
12 | ISS-012 | 2026-01-07 | Training materials not ready for UAT users | Training | 3 | 3 | 9 | Medium | L&D Lead | 2026-01-10 | 2026-01-10 | Materials completed — distributed | Resolved
13 | ISS-013 | 2026-01-08 | Stakeholder not approving test outputs | Governance | 3 | 2 | 6 | Medium | PM | 2026-01-12 | 2026-01-11 | Escalated to sponsor — approval obtained | Resolved
14 | ISS-014 | 2026-01-08 | Meeting room unavailable for workshops | Logistics | 2 | 3 | 6 | Medium | Admin | 2026-01-09 | 2026-01-09 | Alternative venue booked | Resolved
15 | ISS-015 | 2026-01-09 | Report formatting incorrect in new system | Quality | 2 | 2 | 4 | Low | Dev Team | 2026-01-20 |  | Fix logged in backlog — sprint 4 | Planned | Non-critical cosmetic
16 | ISS-016 | 2026-01-09 | User documentation has broken links | Documentation | 2 | 2 | 4 | Low | BA | 2026-01-15 |  | Links being updated | In Progress
17 | ISS-017 | 2026-01-10 | Test environment not matching production | Technology | 3 | 2 | 6 | Medium | DevOps | 2026-01-12 | 2026-01-12 | Environments synced — config matched | Resolved
18 | ISS-018 | 2026-01-10 | Change request backlog growing — 8 pending | Scope | 2 | 2 | 4 | Low | PM | 2026-01-20 |  | Triage session scheduled | Planned | 8 CRs to be prioritised
19 | ISS-019 | 2026-01-11 | Performance degradation after data migration | Technology | 3 | 3 | 9 | Medium | DBA | 2026-01-15 |  | Index rebuild in progress | In Progress | DB optimisation underway
20 | ISS-020 | 2026-01-11 | Project board quorum not met last meeting | Governance | 2 | 2 | 4 | Low | Company Sec | 2026-01-20 |  | Quorum rules being enforced | In Progress | Attendance rules circulated

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit