## Feasibility Assessment
Project Feasibility Assessment
Evaluate project feasibility across strategic, financial, technical, operational, and risk dimensions before approval
S.No. | Assessment Area | Criteria | Weight % | Score (1-5) | Weighted Score | Finding | Risk Level | Recommendation
1 | Strategic Fit | Alignment with company strategy | 15% | 5 | 0.75 | Fully aligned with 2026 growth plan | Low | Proceed
2 | Strategic Fit | Market opportunity and demand | 10% | 4 | 0.40 | Strong UAE market demand confirmed | Low | Proceed
3 | Strategic Fit | Competitive advantage | 10% | 4 | 0.40 | First-mover advantage in niche segment | Low | Proceed
4 | Financial | Expected ROI | 15% | 4 | 0.60 | Projected 35% ROI over 3 years | Medium | Proceed with monitoring
5 | Financial | Payback period | 10% | 3 | 0.30 | 18-month payback — acceptable | Medium | Proceed
6 | Financial | Funding availability | 10% | 5 | 0.50 | Full budget approved and allocated | Low | Proceed
7 | Technical | Technology readiness | 10% | 3 | 0.30 | Some technology gaps — training needed | Medium | Mitigate before start
8 | Technical | Infrastructure requirements | 5% | 4 | 0.20 | Existing infrastructure sufficient | Low | Proceed
9 | Operational | Resource availability | 5% | 3 | 0.15 | 2 key roles need to be hired | Medium | Hire before go-live
10 | Operational | Process impact | 5% | 4 | 0.20 | Minimal disruption to current operations | Low | Proceed
11 | Legal & Compliance | Regulatory requirements | 5% | 5 | 0.25 | All required licenses in place | Low | Proceed
12 | Legal & Compliance | Contract and IP considerations | 5% | 4 | 0.20 | IP protected — NDA signed with partners | Low | Proceed
13 | Risk | Overall project risk rating | 5% | 3 | 0.15 | Medium risk — manageable with controls | Medium | Proceed with risk plan
14 | Risk | Dependency on external parties | 5% | 3 | 0.15 | 2 key vendor dependencies identified | Medium | Dual-source strategy
15 | Stakeholder | Executive sponsorship | 5% | 5 | 0.25 | CEO and board fully committed | Low | Proceed
16 | Stakeholder | End-user acceptance likelihood | 5% | 4 | 0.20 | Pilot group positive — change plan needed | Medium | Proceed with change mgmt
17 | Timeline | Schedule feasibility | 5% | 4 | 0.20 | 12-month timeline achievable | Low | Proceed
18 | Timeline | Dependencies and critical path | 5% | 3 | 0.15 | 3 external dependencies on critical path | Medium | Monitor closely
19 | Sustainability | Environmental impact | 5% | 5 | 0.25 | Net zero impact — green initiative | Low | Proceed
20 | Sustainability | Long-term viability | 5% | 4 | 0.20 | 5-year outlook positive | Low | Proceed

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit