## Assumptions Log
Project Assumptions Log
Log and validate all project assumptions — category, impact if wrong, probability, validation status, and outcomes
S.No. | Assumption ID | Date Logged | Category | Assumption Statement | Basis / Rationale | Impact if Wrong | Probability | Owner | Validation Date | Validated | Outcome | Status | Notes
1 | ASS-001 | 2026-01-02 | Resources | All 5 dev resources will be available for full project duration | Resource plan confirmed by HR | Timeline extends by 30% | Medium | HR Manager | 2026-01-15 | Partial | 1 developer resigned — replaced | At Risk | Mitigation: contractor backup
2 | ASS-002 | 2026-01-02 | Budget | Budget of AED 2.5M will remain unchanged throughout project | Board approval received | Scope reduction required | Low | CFO | 2026-01-10 | Yes | Budget confirmed — no change | Valid
3 | ASS-003 | 2026-01-02 | Technology | Existing ERP can integrate with new CRM without major rework | IT assessment done Nov 2025 | 6-week delay + AED 200K extra | Medium | Tech Lead | 2026-01-20 | No | Integration more complex than expected | Invalid | Change request raised
4 | ASS-004 | 2026-01-02 | Stakeholders | All department heads will participate in UAT | HOD commitment obtained in kickoff | UAT fails — poor coverage | Low | PM | 2026-02-15 | Pending | Awaiting UAT phase | Pending | UAT starts Feb
5 | ASS-005 | 2026-01-03 | Vendor | Vendor will deliver module on time per contract | Contractual SLA in place | Project delayed by 3 weeks | Medium | Procurement | 2026-02-15 | Pending | Vendor tracking to schedule | On Track | Monitor weekly
6 | ASS-006 | 2026-01-03 | Regulatory | No new regulatory requirements will affect scope | Legal review done Dec 2025 | Rework required | Low | Legal Counsel | 2026-03-31 | Pending | No changes expected | Valid | Annual legal review scheduled
7 | ASS-007 | 2026-01-03 | Data | All historical data can be migrated without transformation | Data assessment done | Extra 2 weeks for cleansing | High | Data Architect | 2026-02-28 | No | 30% of data needs transformation | Invalid | Data sprint added to plan
8 | ASS-008 | 2026-01-04 | Infrastructure | Current server capacity is sufficient for new system | IT capacity report | Performance issues at go-live | Medium | IT Manager | 2026-01-31 | No | Servers need upgrade | Invalid | Cloud migration approved
9 | ASS-009 | 2026-01-04 | Training | 2-day training will be sufficient for end users | L&D assessment | Low adoption rate | Medium | L&D Lead | 2026-02-28 | Pending | Training not yet delivered | Pending | Consider extended training
10 | ASS-010 | 2026-01-05 | Timeline | UAT can be completed in 3 weeks | Based on similar past projects | Go-live delayed | High | PM | 2026-02-28 | Pending | UAT plan in progress | Pending | May need 5 weeks based on scope
11 | ASS-011 | 2026-01-05 | Business | Business processes will not change during implementation | Process owner confirmation | Rework on requirements | Medium | BA | 2026-01-31 | Partial | Minor changes in finance process | At Risk | Change request pending
12 | ASS-012 | 2026-01-06 | Resources | Key business SMEs will give 20% of their time to project | HOD agreement | Inadequate input — delays | High | PM | 2026-01-15 | No | SMEs only able to give 10% | Invalid | Scope SME involvement carefully
13 | ASS-013 | 2026-01-06 | Vendor | Third-party API will be stable for integration | Vendor SLA documentation | Integration failures | Low | Tech Lead | 2026-02-28 | Pending | API testing not started | Pending | Test in Feb
14 | ASS-014 | 2026-01-07 | Security | Security audit will clear before go-live | Pen test scheduled Feb | Go-live delayed | Medium | IT Security | 2026-02-28 | Pending | Pen test not yet done | Pending
15 | ASS-015 | 2026-01-07 | Budget | Contingency of 10% is sufficient | Industry standard | Over-budget | Medium | CFO | 2026-03-31 | Pending | No contingency drawn yet | Valid | Monitor monthly
16 | ASS-016 | 2026-01-08 | Users | End users will embrace the new system | Change readiness survey positive | Resistance and low adoption | Medium | Change Mgr | 2026-03-31 | Pending | Change programme running | On Track
17 | ASS-017 | 2026-01-08 | Legal | Data can be transferred to cloud without legal restriction | Legal opinion obtained | Data cannot move to cloud | Low | Legal Counsel | 2026-01-31 | Yes | Cloud data transfer approved | Valid
18 | ASS-018 | 2026-01-09 | Technology | Mobile app can be delivered within current sprint plan | Development team estimate | App delayed 4 weeks | Medium | Tech Lead | 2026-02-28 | Pending | Mobile dev 60% complete | On Track
19 | ASS-019 | 2026-01-09 | Stakeholders | Executive sponsor will remain in role throughout project | Confirmed by CEO office | Loss of sponsorship | Low | PM | 2026-12-31 | Pending | Sponsor active and engaged | Valid
20 | ASS-020 | 2026-01-10 | Budget | Licence costs will not increase at renewal | Vendor price lock for 12 months | Budget shortfall | Low | CFO | 2026-06-30 | Pending | Vendor confirmed pricing | Valid | Check at renewal

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit