## Charter Checklist
Project Charter Checklist
Complete all project charter requirements before kickoff — objectives, scope, stakeholders, team, budget, timeline, risks, and sign-offs
S.No. | Section | Checklist Item | Owner | Status | Date Completed | Notes
1 | Objectives | Business case documented and approved | Sponsor | Done | 2026-01-05 | Signed off by CEO
2 | Objectives | Project objectives are SMART | PM | Done | 2026-01-05 | 3 objectives defined
3 | Objectives | Success criteria defined and agreed | PM + Sponsor | Done | 2026-01-05 | KPIs signed off
4 | Scope | In-scope items listed and agreed | PM + BA | Done | 2026-01-06 | Scope doc v1.0
5 | Scope | Out-of-scope items explicitly stated | PM + BA | Done | 2026-01-06 | 3 items excluded
6 | Scope | Assumptions documented | PM | Done | 2026-01-06 | 12 assumptions logged
7 | Scope | Constraints documented | PM | Done | 2026-01-06 | Budget and timeline
8 | Stakeholders | Stakeholder register completed | PM | Done | 2026-01-07 | 18 stakeholders identified
9 | Stakeholders | Project sponsor formally identified | PMO | Done | 2026-01-05 | CEO is sponsor
10 | Stakeholders | Project steering committee defined | PMO | Done | 2026-01-07 | 5 members confirmed
11 | Team | Project manager formally appointed | Sponsor | Done | 2026-01-05 | Ahmed Al Rashid
12 | Team | Core team roles identified | PM | Done | 2026-01-07 | 8 roles confirmed
13 | Team | RACI matrix completed | PM | In Progress |  | Draft shared for review
14 | Budget | Total budget approved | CFO | Done | 2026-01-06 | AED 2.5M approved
15 | Budget | Contingency reserve agreed | CFO | Done | 2026-01-06 | 10% contingency
16 | Budget | Procurement authority levels set | CFO | In Progress |  | Pending policy update
17 | Timeline | High-level milestone plan approved | PM + Sponsor | Done | 2026-01-08 | 5 milestones agreed
18 | Timeline | Project end date confirmed | Sponsor | Done | 2026-01-08 | 31 Dec 2026
19 | Risks | Initial risk register created | PM | Done | 2026-01-08 | 10 risks identified
20 | Sign-off | Project charter signed by sponsor and PM | Both | Done | 2026-01-10 | Charter v1.0 signed

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit