## Earned Value Analysis (EVM)
Earned Value Analysis (EVM)
SPI, CPI, EAC and VAC calculations for project performance tracking
Parameter | Value | Formula | Interpretation | Status
PROJECT EVM DATA
Budget at Completion (BAC) | ₹38,22,500 | Total approved budget | Total project budget | Set
Planned Value (PV) | ₹22,00,000 | BAC × % planned complete | Work planned by today | Calculated
Earned Value (EV) | ₹20,90,000 | BAC × % actual complete | Work actually done (value) | Calculated
Actual Cost (AC) | ₹21,50,000 | Actual costs incurred | Money actually spent | Actual
PERFORMANCE INDICES
Schedule Variance (SV) | - ₹1,10,000 | EV - PV | Negative = Behind schedule | 🟡 Behind
Cost Variance (CV) | - ₹60,000 | EV - AC | Negative = Over budget | 🟡 Over
Schedule Performance Index (SPI) | 0.95 | EV ÷ PV | <1 = Behind schedule | 🟡 Watch
Cost Performance Index (CPI) | 0.97 | EV ÷ AC | <1 = Over budget | 🟡 Watch
FORECASTING
Estimate at Completion (EAC) | ₹39,40,206 | BAC ÷ CPI | Forecast total cost at current CPI | 🟡 Over BAC
Estimate to Complete (ETC) | ₹17,90,206 | EAC - AC | Remaining work cost forecast | Calculated
Variance at Completion (VAC) | -₹1,17,706 | BAC - EAC | Positive = Under budget at end | 🟡 At Risk
To-Complete Performance Index (TCPI) | 1.03 | (BAC-EV)÷(BAC-AC) | Need CPI >1 to finish on budget | 🟡 Tight
SUMMARY
Overall Assessment | Slight overrun | Review at next SteerCo | Both SPI and CPI just below 1.0 | 🟡 Monitor
Recommended Action | Cost reduction | Reduce scope or increase budget | Discuss with sponsor | PM Action

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit