## Risk & Issue Summary
Risk & Issue Summary Report
Consolidated view of all open risks and issues — track likelihood, impact, ownership and mitigation actions
# | ID | Type | Title | Description | Category | Probability | Impact | Risk Score | Owner | Mitigation / Resolution | Date Raised | Target Date | Status
1 | R-001 | Risk | Key resource resignation | Senior developer may resign before go-live | Resource | Medium | High | High | PM / HR | Identify backup; cross-train team member | 01-Jun-25 | 30-Jun-25 | Open
2 | R-002 | Risk | Vendor delivery delay | Primary hardware vendor may miss delivery SLA | Procurement | High | High | Critical | Procurement Lead | Engage alternate vendor; add SLA penalties to contract | 05-Jun-25 | 20-Jun-25 | In Progress
3 | R-003 | Risk | Scope creep from client | Client may request features outside agreed scope | Scope | High | Medium | High | Project Manager | Strict change control process; weekly scope review | 01-Jun-25 | Ongoing | Open
4 | R-004 | Risk | Budget overrun | Unplanned procurement costs may exceed contingency | Finance | Low | High | Medium | Finance Manager | Weekly budget review; pre-approve all purchases >AED 5,000 | 10-Jun-25 | Ongoing | Monitoring
5 | R-005 | Risk | Data migration errors | Legacy data may not map cleanly to new system | Technical | Medium | High | High | Dev Lead | Run data migration dry-run in UAT environment | 12-Jun-25 | 25-Jun-25 | In Progress
6 | I-001 | Issue | UAT environment not ready | Test environment setup delayed by 5 days | Technical | — | High | — | IT Admin | Expedite environment provisioning; escalated to IT Head | 15-Jun-25 | 20-Jun-25 | In Progress
7 | I-002 | Issue | Stakeholder unavailable for sign-off | Key stakeholder on leave during sign-off window | Governance | — | Medium | — | PM | Delegate sign-off authority to deputy; get written confirmation | 18-Jun-25 | 22-Jun-25 | Open
8 | I-003 | Issue | Integration API failing in testing | Third-party API returns errors in 20% of calls | Technical | — | High | — | Dev Lead | Vendor engaged; workaround implemented for critical flows | 17-Jun-25 | 24-Jun-25 | In Progress

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit