## Escalation Log
Issue Escalation Log
Track all project issue escalations — severity, escalation path, resolution actions, and closure status
S.No. | Issue ID | Date Raised | Issue Title | Description | Raised By | Assigned To | Severity | Escalated To | Escalation Date | Resolution | Resolved Date | Status | Remarks
1 | ESC-001 | 2026-01-03 | Budget Overrun Risk | Costs tracking 15% above baseline | PM | CFO | High | CEO | 2026-01-04 | Budget reallocated from contingency | 2026-01-08 | Resolved | AED 200K from contingency
2 | ESC-002 | 2026-01-05 | Key Resource Resignation | Senior dev resigned mid-project | HR Manager | PM | Critical | CEO + Sponsor | 2026-01-05 | Contractor hired as replacement | 2026-01-12 | Resolved | 2-week gap managed
3 | ESC-003 | 2026-01-07 | Vendor Delivery Delay | Vendor 3 weeks behind schedule | PM | Procurement | High | COO | 2026-01-08 | Penalty clause invoked, plan revised | 2026-01-15 | Resolved | Timeline adjusted
4 | ESC-004 | 2026-01-08 | Scope Creep | 10 new requirements added post-sign-off | BA | Sponsor | High | Steering Committee | 2026-01-10 | Change request raised and approved | 2026-01-18 | Resolved | CR-005 raised
5 | ESC-005 | 2026-01-10 | Integration Failure | API integration failing in test env | Tech Lead | DevOps | Critical | CTO | 2026-01-10 | Rollback applied, root cause fixed | 2026-01-14 | Resolved | Hotfix deployed
6 | ESC-006 | 2026-01-12 | Stakeholder Conflict | Two departments disagree on process | BA | PM | Medium | Sponsor | 2026-01-13 | Workshop held — agreed on approach | 2026-01-16 | Resolved | Decision logged
7 | ESC-007 | 2026-01-14 | Data Quality Issue | Source data has 30% error rate | Data Analyst | Tech Lead | High | CTO + Business | 2026-01-15 | Data cleansing sprint added | 2026-01-22 | Resolved | Extra 1-week sprint
8 | ESC-008 | 2026-01-15 | Security Vulnerability | Pen test found critical vulnerability | IT Security | DevOps | Critical | CTO + CEO | 2026-01-15 | Patch applied and re-tested | 2026-01-18 | Resolved | Emergency patch
9 | ESC-009 | 2026-01-17 | UAT Sign-off Delay | Business refusing to sign off UAT | PM | Business Owner | High | Sponsor | 2026-01-18 | Issues list resolved — sign-off done | 2026-01-25 | Resolved | 18 defects fixed
10 | ESC-010 | 2026-01-18 | License Procurement Delay | Critical software license not received | IT Manager | Procurement | High | COO | 2026-01-19 | Emergency purchase approved | 2026-01-21 | Resolved | Express delivery
11 | ESC-011 | 2026-01-20 | Go-Live Date at Risk | 3 critical defects still open | PM | Tech Lead | Critical | Sponsor + CEO | 2026-01-20 | Go-live delayed by 1 week |  | In Progress | New date 1 Feb 2026
12 | ESC-012 | 2026-01-21 | Training Resource Conflict | L&D team double-booked | PM | HR Manager | Medium | COO | 2026-01-22 | External trainer engaged | 2026-01-25 | Resolved
13 | ESC-013 | 2026-01-22 | Change Resistance | End users resisting new system | Change Lead | HR + Sponsor | Medium | CEO | 2026-01-23 | Change comms plan reinforced |  | In Progress | Town hall scheduled
14 | ESC-014 | 2026-01-23 | Infrastructure Capacity | Prod servers at 90% — need upgrade | DevOps | IT Manager | High | CTO | 2026-01-23 | Cloud capacity added | 2026-01-25 | Resolved | AWS scale-up
15 | ESC-015 | 2026-01-25 | Regulatory Approval Delay | Awaiting DED approval for 3 weeks | Legal | Legal Counsel | High | CEO | 2026-01-25 | Direct engagement with DED |  | In Progress | Meeting arranged
16 | ESC-016 | 2026-01-26 | Project Documentation Gap | Key docs not updated for audit | PMO | PM | Medium | PMO Director | 2026-01-26 | Doc sprint completed | 2026-01-29 | Resolved | All docs updated
17 | ESC-017 | 2026-01-27 | Payment Dispute with Vendor | Vendor disputing milestone payment | Finance | Procurement | Medium | CFO | 2026-01-27 | Legal review — payment held |  | In Progress | Dispute ongoing
18 | ESC-018 | 2026-01-28 | Environment Outage | Test env down for 8 hours | DevOps | IT Manager | High | CTO | 2026-01-28 | Root cause fixed — monitoring added | 2026-01-28 | Resolved | Same-day fix
19 | ESC-019 | 2026-01-29 | Sponsor Availability | Sponsor unavailable for 2 weeks | PM | CEO Office | Medium | CEO | 2026-01-29 | Delegate authority given to COO | 2026-01-30 | Resolved
20 | ESC-020 | 2026-01-30 | Post Go-Live Defect | Critical defect found after go-live | Support Team | Tech Lead | Critical | CTO + Sponsor | 2026-01-30 | Hotfix in progress — ETA 48 hrs |  | In Progress | P1 — all hands on deck

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit