## Budget Variance
Project Budget Variance Report
Track project budget vs actual spend by cost category — monthly actuals, Q1 variance, forecast to complete, and EAC
S.No. | Category | Work Package | Approved Budget | Jan Actual | Feb Actual | Mar Actual | Q1 Actual | Q1 Budget | Q1 Variance | Var % | Forecast to Complete | EAC | Status | Notes
1 | Labour | Project Management | 180000 | 15000 | 15000 | 15000 | 45000 | 45000 | 0 | 0% | 135000 | 180000 | On Budget | Fixed monthly
2 | Labour | Business Analysis | 120000 | 18000 | 12000 | 12000 | 42000 | 30000 | -12000 | -40% | 78000 | 120000 | Over Budget | Extra workshop added
3 | Labour | Development Team | 480000 | 38000 | 42000 | 45000 | 125000 | 120000 | -5000 | -4% | 360000 | 485000 | Slight Over | Minor OT costs
4 | Labour | QA Testing | 160000 | 8000 | 15000 | 18000 | 41000 | 40000 | -1000 | -3% | 120000 | 161000 | On Budget
5 | Labour | DevOps | 80000 | 6500 | 6500 | 7000 | 20000 | 20000 | 0 | 0% | 60000 | 80000 | On Budget
6 | Labour | Change Management | 60000 | 5000 | 5000 | 5000 | 15000 | 15000 | 0 | 0% | 45000 | 60000 | On Budget
7 | Technology | Software Licenses | 95000 | 45000 | 0 | 0 | 45000 | 45000 | 0 | 0% | 50000 | 95000 | On Budget | Annual upfront
8 | Technology | Cloud Infrastructure | 48000 | 3800 | 4200 | 4500 | 12500 | 12000 | -500 | -4% | 36000 | 48500 | Slight Over | Usage higher
9 | Technology | Dev Tools | 18000 | 1500 | 1500 | 1500 | 4500 | 4500 | 0 | 0% | 13500 | 18000 | On Budget
10 | External | Vendor TechArabia | 250000 | 0 | 60000 | 0 | 60000 | 62500 | 2500 | 4% | 187500 | 247500 | Under Budget | Milestone 1 paid
11 | External | Training Provider | 45000 | 0 | 0 | 22000 | 22000 | 0 | -22000 | N/A | 23000 | 45000 | Ahead | Training started early
12 | External | Legal Counsel | 30000 | 2500 | 2500 | 2500 | 7500 | 7500 | 0 | 0% | 22500 | 30000 | On Budget
13 | External | Security Audit | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 25000 | 25000 | On Budget | Scheduled Q2
14 | Contingency | Risk Contingency | 120000 | 0 | 0 | 8000 | 8000 | 0 | -8000 | N/A | 112000 | 120000 | Used | Scope change CR-001
15 | Overhead | Project Office | 35000 | 2800 | 2800 | 2800 | 8400 | 8750 | 350 | 4% | 26600 | 35000 | On Budget
16 | Overhead | Travel and Expenses | 20000 | 1200 | 1800 | 1500 | 4500 | 5000 | 500 | 10% | 15500 | 20000 | Under Budget | Less travel needed
17 | Overhead | Communication | 12000 | 850 | 850 | 850 | 2550 | 3000 | 450 | 15% | 9450 | 12000 | Under Budget | Digital comms cheaper
18 | Overhead | Printing and Materials | 8000 | 300 | 400 | 350 | 1050 | 2000 | 950 | 48% | 6950 | 8000 | Under Budget | Went digital
19 | Overhead | Miscellaneous | 15000 | 580 | 720 | 650 | 1950 | 3750 | 1800 | 48% | 13050 | 15000 | Under Budget | Minimal misc spend
20 | TOTAL | Project Total | 1801000 | 149030 | 170270 | 147650 | 466950 | 423500 | -43450 | -10% | 1338550 | 1805550 | Slight Over | AED 4.5K above budget

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit