## Change Impact
Change Impact Assessment
Assess the people, process, and technology impact of all organisational changes — readiness, risks, mitigations, and communication plans
S.No. | Change Ref | Change Title | Change Type | Departments Affected | People Impacted | Process Impact | Technology Impact | Culture Impact | Impact Level | Readiness Score | Key Risks | Mitigation Actions | Communication Plan | Training Required | Status
1 | CIA-001 | New ERP System Go-Live | Technology | Finance, HR, Ops, Sales | 420 | Full process redesign in all depts | Complete system replacement | High — new ways of working | High | 42% | Resistance from long-tenured staff | Change champions — 1 per dept | All-staff town halls x3 | Yes — 3 days | In Progress
2 | CIA-002 | Hybrid Work Policy | Policy | All departments | 285 | Flexible scheduling new norm | VPN and collaboration tools | Shift in team culture expected | Medium | 65% | Inequality concerns — office vs home | Clear policy and FAQ document | Policy email + manager briefing | No | Done
3 | CIA-003 | Finance Module Upgrade | Process | Finance | 35 | Month-end process changes | New GL and reporting module | Low — same team | Medium | 58% | Month-end disruption risk | Parallel run for 2 months | Finance team briefings x4 | Yes — 1 day | In Progress
4 | CIA-004 | Sales CRM Migration | Technology | Sales, Marketing | 85 | All opportunity tracking changes | New CRM platform — Salesforce | Pipeline visibility improves | High | 48% | Data loss fear — sales resistance | Data migration validation plan | Sales team demos x2 | Yes — 2 days | Planned
5 | CIA-005 | Org Restructure — Sales | People | Sales | 45 | New team structure and reporting lines | CRM hierarchy changes | Uncertainty — morale risk | High | 35% | Talent flight risk during change | 1:1 conversations with all staff | Announcement by CEO direct | No | Planned
6 | CIA-006 | Paperless AP Process | Process | Finance, Procurement | 28 | Invoice approval fully digital | AP automation software | Low cultural impact | Low | 72% | Some staff prefer paper process | Training and benefit comms | Process guide email | Yes — half day | Done
7 | CIA-007 | KSA Office Opening | Strategic | Sales, HR, Legal | 15 | New remote team management | KSA systems and VPN access | Cultural sensitivity needed | Medium | 55% | Cross-cultural friction risk | Cultural awareness training | KSA team announcements | Yes — 1 day | In Progress
8 | CIA-008 | Customer Portal Launch | Technology | Customer Success, IT | 60 | New self-service workflows | Customer portal integration | CS team empowered | Medium | 62% | Customer adoption uncertain | Beta testing with top clients | Client webinar x2 | Yes — 1 day | Planned
9 | CIA-009 | ISO 27001 Certification | Compliance | IT, Legal, All depts | 285 | New security policies and procedures | Security tool deployment | Security-first mindset shift | Medium | 50% | Compliance fatigue from staff | Quick wins and visible benefits | Awareness campaign 3 months | Yes — 2 hrs | In Progress
10 | CIA-010 | Salary Benchmarking Revision | People | HR, Finance | 285 | New pay bands affect all staff | HRIS update required | Morale boost expected | Medium | 68% | Underpaid staff may still leave | Transparent communication plan | 1:1 manager sessions | No | Planned
11 | CIA-011 | Supply Chain Digitalisation | Technology | Operations, Procurement | 55 | End-to-end digital tracking new | New SCM software | Efficiency mindset shift | High | 40% | Vendor resistance to change | Vendor briefing sessions | Ops team workshop x2 | Yes — 2 days | Planned
12 | CIA-012 | Brand Refresh | Marketing | Marketing, Sales | 45 | New templates and brand guidelines | Design assets replacement | Pride in new brand expected | Low | 80% | Staff slow to adopt new brand | Brand guide and asset library | Marketing all-hands | No | Done
13 | CIA-013 | AI Tools Rollout | Technology | All departments | 285 | AI-assisted workflows across depts | ChatGPT, Copilot deployment | Fear of job loss — manage | High | 38% | Change resistance — AI fear | AI champion training programme | CEO vision speech + comms | Yes — 1 day | Planned
14 | CIA-014 | Expense Policy Tightening | Policy | All departments | 285 | New limits and approval workflow | Finance system update | Minor grumbling expected | Low | 75% | Managers resent new approval flow | Clear rationale communication | HOD briefing + policy email | No | Done
15 | CIA-015 | Data Centre Migration to Cloud | Technology | IT | 12 | Monitoring and support approach changes | All servers migrated to AWS | IT team empowered | Medium | 60% | Service disruption during migration | Detailed cut-over plan | IT team briefings | Yes — 2 days | In Progress
16 | CIA-016 | New Performance Framework | People | All departments, HR | 285 | Annual appraisal process redesigned | HRIS performance module | Culture of feedback improves | High | 45% | Fear of transparent feedback | Manager training programme | All-staff comms + workshop | Yes — 1 day | Planned
17 | CIA-017 | WPS Payroll System Upgrade | Technology | HR, Finance | 8, | Payroll processing changes | New WPS-compliant payroll engine | Low — back-office change | Medium | 65% | Payroll errors during transition | Parallel run — 2 months | Payroll team briefing | Yes — 1 day | Planned
18 | CIA-018 | Green Procurement Policy | Policy | Procurement | 15 | New supplier ESG criteria | Supplier evaluation update | ESG mindset shift in team | Low | 70% | Supplier pushback on ESG reqs | Supplier awareness programme | Procurement team briefing | No | Planned
19 | CIA-019 | Shared Services Centre | Strategic | Finance, HR, IT | 85 | Centralised back-office functions | Shared systems and processes | Role clarity needed | High | 35% | Resistance from HODs losing staff | Clear RACI and benefit comms | HOD workshop + CEO support | Yes — 1 day | Planned
20 | CIA-020 | Digital Learning Platform | Technology | HR, All depts | 285 | All training moves online | LMS deployment | Self-directed learning culture | Medium | 58% | Low completion rates risk | Gamification and incentives | Launch campaign + comms | Yes — half day | Planned

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit