## Work Breakdown Structure (WBS)
Work Breakdown Structure (WBS)
Hierarchical decomposition of all project work into manageable tasks
WBS ID | Work Package | Level | Parent | Owner | Duration | Start | End | Status | Notes
1.0 | PROJECT NAME | L1 | — | PM | 180d | 2026-01-01 | 2026-06-30 | Active
1.1 | Initiation Phase | L2 | 1.0 | PM | 14d | 2026-01-01 | 2026-01-14 | Done
1.1.1 | Project Charter | L3 | 1.1 | PM | 5d | 2026-01-01 | 2026-01-05 | Done | Approved
1.1.2 | Stakeholder Register | L3 | 1.1 | PM | 3d | 2026-01-06 | 2026-01-08 | Done
1.1.3 | Kickoff Meeting | L3 | 1.1 | PM | 1d | 2026-01-14 | 2026-01-14 | Done
1.2 | Planning Phase | L2 | 1.0 | PM | 21d | 2026-01-15 | 2026-02-04 | Done
1.2.1 | Develop WBS | L3 | 1.2 | PM | 3d | 2026-01-15 | 2026-01-17 | Done
1.2.2 | Create Gantt Chart | L3 | 1.2 | PM | 3d | 2026-01-18 | 2026-01-20 | Done
1.2.3 | Risk Register | L3 | 1.2 | Risk Lead | 5d | 2026-01-21 | 2026-01-25 | Done
1.2.4 | Budget Baseline | L3 | 1.2 | Finance | 5d | 2026-01-26 | 2026-01-30 | Done
1.3 | Execution Phase | L2 | 1.0 | PM | 90d | 2026-02-05 | 2026-05-05 | Active
1.3.1 | Design | L3 | 1.3 | Design Lead | 30d | 2026-02-05 | 2026-03-06 | Done
1.3.2 | Development | L3 | 1.3 | Dev Lead | 45d | 2026-03-07 | 2026-04-20 | Active
1.3.3 | Testing | L3 | 1.3 | QA Lead | 15d | 2026-04-21 | 2026-05-05 | Pending
1.4 | Closure Phase | L2 | 1.0 | PM | 14d | 2026-05-06 | 2026-05-20 | Pending
1.4.1 | UAT Sign-off | L3 | 1.4 | PM | 5d | 2026-05-06 | 2026-05-10 | Pending
1.4.2 | Lessons Learned | L3 | 1.4 | PM | 3d | 2026-05-11 | 2026-05-13 | Pending
1.4.3 | Project Closure Report | L3 | 1.4 | PM | 3d | 2026-05-14 | 2026-05-16 | Pending
1.4.4 | Handover & Sign-off | L3 | 1.4 | Sponsor | 2d | 2026-05-17 | 2026-05-18 | Pending

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit