## Resource Allocation
Resource Allocation Tracker
Plan and monitor team member allocation, availability and workload across project tasks
# | Resource Name | Role / Designation | Department | Project / Task Assigned | Allocation % | Start Date | End Date | Total Days | Availability | Skills | Remarks
1 | Ahmed Al Mansouri | Project Manager | PMO | Overall Project Management | 100% | 01-Jun-25 | 31-Aug-25 | 65 | Fully Allocated | PMP, Leadership, MS Project
2 | Priya Sharma | Business Analyst | IT | Requirements & UAT | 80% | 01-Jun-25 | 15-Aug-25 | 53 | 20% Available | CBAP, Agile, JIRA | 20% on BAU support
3 | John Mathews | Lead Developer | IT | System Development – Core | 100% | 01-Jun-25 | 31-Jul-25 | 43 | Fully Allocated | Java, SQL, REST APIs
4 | Sara Khalid | Developer | IT | System Development – UI | 100% | 15-Jun-25 | 31-Jul-25 | 34 | Fully Allocated | React, CSS, HTML5 | On leave 05–09 Jul
5 | Ravi Nair | QA Engineer | QA | Testing & Quality Assurance | 100% | 01-Jul-25 | 20-Aug-25 | 36 | Available from 01-Jul | Selenium, Manual Testing
6 | Fatima Al Zaabi | Finance Analyst | Finance | Budget Monitoring & Reporting | 30% | 01-Jun-25 | 31-Aug-25 | 65 | 70% Available | Excel, SAP, Financial Reporting | Part-time involvement
7 | Mark Thompson | Infrastructure Lead | IT Ops | Server Setup & Config | 60% | 15-Jun-25 | 15-Jul-25 | 23 | 40% Available | AWS, Azure, Linux | Shared with IT Ops team
8 | Nadia Hassan | Change Manager | HR | Training & Change Adoption | 50% | 01-Jul-25 | 31-Aug-25 | 44 | 50% Available | PROSCI, Training Design
9 | Carlos Fernandez | Procurement Officer | Procurement | Vendor Management | 40% | 01-Jun-25 | 30-Jun-25 | 22 | 60% Available | Procurement, Contract Mgmt | Closing June engagement
10 | Lisa Wong | PMO Analyst | PMO | Reporting & Documentation | 70% | 01-Jun-25 | 31-Aug-25 | 65 | 30% Available | MS Office, Power BI, SharePoint

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit