## Communication Plan
Project Communication Plan
Define and track all project stakeholder communications — frequency, channel, owner, format, and next scheduled date
S.No. | Stakeholder | Role | Information Need | Communication Type | Frequency | Channel | Owner | Format | Next Date | Status | Notes
1 | Project Sponsor | Sponsor | Project status, risks, decisions needed | Status Report | Monthly | Email | PM | PDF Report | 2026-01-31 | Active | Board pack included
2 | Steering Committee | Governance | Milestone progress, budget, issues | Steering Deck | Monthly | Meeting | PM | PowerPoint | 2026-01-20 | Active | 30-min slot in SC meeting
3 | Project Team | Delivery | Tasks, priorities, blockers | Standup | Daily | Teams | PM | Verbal/Notes | 2026-01-06 | Active | 15-min daily call
4 | Business Stakeholders | End Users | Progress, training dates, go-live plans | Newsletter | Bi-weekly | Email | PM | Email | 2026-01-12 | Active | Keep it brief and clear
5 | IT Department | Technical | Technical specs, dependencies, access needs | Technical Review | Weekly | Meeting | Tech Lead | Agenda/Notes | 2026-01-08 | Active | Friday 10am slot
6 | Finance Team | Financial | Budget status, invoices, forecasts | Budget Report | Monthly | Email | PM | Excel | 2026-01-31 | Active
7 | HR Department | People | Resource allocation, training, onboarding | HR Update | Bi-weekly | Email | PM | Email | 2026-01-12 | Active
8 | External Vendors | Supplier | Deliverables, milestones, payments | Vendor Review | Weekly | Meeting | Procurement | Agenda/MOM | 2026-01-09 | Active | Monday 2pm
9 | Legal & Compliance | Governance | Contract status, compliance, risks | Legal Update | Monthly | Email | PM | Email | 2026-01-25 | Active
10 | End Users — Dept A | End Users | System changes, training schedule | Town Hall | Quarterly | Meeting | BA | Presentation | 2026-03-31 | Active | Q1 town hall scheduled
11 | End Users — Dept B | End Users | System changes, training schedule | Town Hall | Quarterly | Meeting | BA | Presentation | 2026-03-31 | Active | Same session as Dept A
12 | CEO / Executive Team | Executive | High-level status, risks, strategic impact | Executive Summary | Monthly | Email | PM | 1-page brief | 2026-01-31 | Active | Keep to 1 page max
13 | Change Manager | Change | Change impact, resistance, readiness | Change Update | Bi-weekly | Meeting | Change Mgr | Change Report | 2026-01-12 | Active
14 | Testing / QA Team | Quality | Test plans, defects, UAT schedule | QA Review | Weekly | Meeting | QA Lead | Agenda/Notes | 2026-01-08 | Active | Wednesday 3pm
15 | Training Team | L&D | Training materials, schedule, readiness | Training Update | Bi-weekly | Email | L&D Lead | Email | 2026-01-12 | Active
16 | Risk Manager | Risk | New risks, risk status, mitigation | Risk Review | Weekly | Meeting | PM | Risk Register | 2026-01-09 | Active | Fridays 11am
17 | PMO | Governance | RAG status, milestones, governance | PMO Report | Weekly | Email | PM | PMO Template | 2026-01-08 | Active | Due every Monday
18 | Communications Team | Comms | Key messages, announcements, comms plan | Comms Briefing | Monthly | Meeting | PM + Comms | Briefing doc | 2026-01-20 | Active
19 | Audit / Internal Audit | Governance | Project governance, controls, compliance | Audit Update | Quarterly | Email | PM | Audit Pack | 2026-03-31 | Active | Q1 audit due Mar
20 | Project Board | Governance | Go/No-Go decisions, exceptions, budget | Project Board | Monthly | Meeting | PM | Board Paper | 2026-01-20 | Active | Formal escalation route

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit