## Home Purchase Checklist
Home Purchase Checklist — Step by Step Guide
Excel Gurukul Online ¦ Real Estate & Property · Buying & Selling
Stage | Task | Responsible | Due Date | Status | Cost Est. (₹) | Notes
1 - Budget & Finance | Calculate total budget (property + stamp duty + reg) | Buyer | Before search | Pending | 0 | Include 7-8% for charges
1 - Budget & Finance | Get home loan pre-approval from bank | Buyer | Week 1 | Pending | 0 | SBI / HDFC / ICICI
1 - Budget & Finance | Check CIBIL credit score (min 750 recommended) | Buyer | Week 1 | Pending | 0 | Free on BankBazaar
2 - Property Search | Shortlist localities & visit sites | Buyer | Week 2-4 | Pending | 0 | Check flood zone, metro proximity
2 - Property Search | Verify RERA registration of project | Buyer/Agent | Week 2-4 | Pending | 0 | rera.karnataka.gov.in
2 - Property Search | Check builder track record & delivery history | Buyer | Week 2-4 | Pending | 0 | NoBroker / 99acres reviews
3 - Legal Verification | Verify title deed & ownership chain (min 30 yrs) | Lawyer | Week 5 | Pending | 15000 | Hire property lawyer
3 - Legal Verification | Check encumbrance certificate (EC) | Lawyer | Week 5 | Pending | 500 | Sub-registrar office
3 - Legal Verification | Verify Khata / property tax paid up to date | Lawyer | Week 5 | Pending | 0 | BBMP / Corporation
3 - Legal Verification | Check approved building plan & occupancy certificate | Lawyer | Week 5 | Pending | 0 | BDA / Local authority
4 - Agreement | Sign sale agreement & pay token advance (1-2%) | Buyer | Week 6 | Pending | 100000 | Notarise the agreement
4 - Agreement | Arrange remaining down payment (20% typical) | Buyer | Week 6-7 | Pending | 1400000 | Bank transfer
5 - Registration | Pay stamp duty (5-6% in Karnataka) | Buyer | Week 8 | Pending | 350000 | Pay at sub-registrar
5 - Registration | Pay registration charges (1%) | Buyer | Week 8 | Pending | 70000
5 - Registration | Complete sale deed registration at sub-registrar | Both + Lawyer | Week 8 | Pending | 5000 | Lawyer fees
6 - Post-Purchase | Apply for Khata transfer in buyer's name | Buyer | Week 9 | Pending | 2000 | BBMP office
6 - Post-Purchase | Update property tax records | Buyer | Week 10 | Pending | 0 | Corporation
6 - Post-Purchase | Arrange home insurance | Buyer | Week 10 | Pending | 8000 | Annual premium approx

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit