## First Time Buyer
First-Time Buyer Checklist
Step-by-step checklist for first-time property buyers — finance, search, offer, legal, transfer, and post-purchase tasks with costs
S.No. | Stage | Task | Description | Responsible | Target Date | Done Date | Status | Cost (AED) | Notes
1 | Finance | Check credit score | Check UAE credit bureau report — Al Etihad | Buyer | 2026-01-05 | 2026-01-05 | Done | 0 | Score: 780 — good
2 | Finance | Calculate affordability | Monthly EMI should not exceed 35% of income | Buyer | 2026-01-05 | 2026-01-05 | Done | 0 | Max EMI: AED 8,750
3 | Finance | Get mortgage pre-approval | Apply to 2-3 banks and get pre-approval letter | Buyer + Banks | 2026-01-10 | 2026-01-08 | Done | 0 | Approved AED 1.2M — Emirates NBD
4 | Finance | Budget for all buying costs | DLD fee 4%, mortgage fee 0.25%, agent 2% | Buyer | 2026-01-08 | 2026-01-08 | Done | 0 | Total costs est. AED 95,000
5 | Finance | Save down payment | Minimum 20% for expats — 15% for UAE nationals | Buyer | 2026-03-01 |  | In Progress | 0 | Target: AED 200K — at AED 150K
6 | Search | Define property criteria | Location, size, type, budget, must-haves | Buyer | 2026-01-10 | 2026-01-10 | Done | 0 | 2BR, 950-1100sqft, Dubai, AED 900-1.1M
7 | Search | Research neighbourhoods | JVC, JBR, Business Bay, Dubai Hills | Buyer | 2026-01-12 | 2026-01-12 | Done | 0 | JVC shortlisted as primary
8 | Search | Engage property agent | Appoint RERA-registered agent | Buyer | 2026-01-12 | 2026-01-12 | Done | 0 | Sara Khalil — Better Homes
9 | Search | View shortlisted properties | View 8-10 properties before deciding | Buyer + Agent | 2026-01-20 | 2026-01-25 | Done | 0 | Viewed 9 properties — 3 shortlisted
10 | Search | Do comparative market analysis | Compare price/sqft vs nearby recent sales | Agent | 2026-01-25 | 2026-01-26 | Done | 0 | Target property fairly priced
11 | Offer | Make an offer | Submit offer — negotiate with seller | Buyer + Agent | 2026-01-27 | 2026-01-28 | Done | 0 | Offered AED 820K — accepted AED 835K
12 | Offer | Sign MOU / Form F | Sign Memorandum of Understanding | Buyer + Seller | 2026-01-29 | 2026-01-30 | Done | 0 | MOU signed — 10% deposit paid
13 | Offer | Pay reservation deposit | 10% of property price — MOU deposit | Buyer | 2026-01-29 | 2026-01-30 | Done | 83500 | AED 83,500 paid
14 | Legal | Hire a conveyancing lawyer | Optional but recommended for first-timers | Buyer | 2026-02-01 | 2026-02-02 | Done | 3500 | Al Tamimi & Co. — AED 3,500
15 | Legal | Request NOC from developer | Developer issues NOC for transfer | Seller | 2026-02-10 |  | In Progress | 0 | Developer: Emaar — processing
16 | Legal | Complete mortgage application | Submit full mortgage docs to bank | Buyer | 2026-02-05 | 2026-02-06 | Done | 0 | Docs submitted — awaiting approval
17 | Legal | Bank property valuation | Bank sends valuer to assess property | Bank | 2026-02-10 | 2026-02-12 | Done | 2000 | Valued at AED 840K — satisfactory
18 | Transfer | Pay DLD transfer fee | 4% of property value — paid at DLD | Buyer | 2026-02-25 |  | Pending | 33400 | AED 33,400 — payable on transfer day
19 | Transfer | Attend DLD transfer | Both buyer and seller attend Dubai Land Dept | Both + Agents | 2026-02-25 |  | Pending | 0 | Appointment booked 25 Feb
20 | Post-Buy | Transfer utilities and insurance | DEWA, du/Etisalat, building insurance | Buyer | 2026-02-28 |  | Pending | 3000 | After handover — arrange all utilities

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit