## Renovation Budget
Property Renovation Budget
Track all property renovation costs by room — contractor quotes, negotiated rates, advances, actual costs, variance, and completion status
S.No. | Room / Area | Work Item | Contractor | Quoted (AED) | Negotiated (AED) | Advance Paid | Balance Due | Start Date | Completion Date | Actual Cost | Variance | Rating | Status | Notes
1 | Kitchen | Full kitchen refit — cabinets and worktop | Gulf Carpentry | 28000 | 25000 | 12500 | 12500 | 2026-02-01 | 2026-02-28 | 24800 | 200 | 5/5 | Done | Under budget — great finish
2 | Kitchen | Sink, taps, plumbing upgrade | Hassan Plumber | 3500 | 3200 | 1600 | 1600 | 2026-02-05 | 2026-02-10 | 3200 | 0 | 5/5 | Done
3 | Kitchen | Electrical — extra sockets and hood | Ali Electrician | 2800 | 2500 | 1250 | 1250 | 2026-02-05 | 2026-02-12 | 2500 | 0 | 4/5 | Done
4 | Kitchen | Floor tiles — 30sqm ceramic | Raj Tiling | 4500 | 4000 | 2000 | 2000 | 2026-02-08 | 2026-02-15 | 4000 | 0 | 5/5 | Done | Pattern tiles — beautiful
5 | Bathrooms | Master bath — full refit | Gulf Carpentry | 15000 | 13500 | 6750 | 6750 | 2026-03-01 | 2026-03-20 | 13500 | 0 | 5/5 | Done | Premium finish
6 | Bathrooms | Bath 2 — tiles and fittings | Gulf Carpentry | 8000 | 7500 | 3750 | 3750 | 2026-03-01 | 2026-03-20 | 7800 | -300 | 4/5 | Done | Slight overrun — material cost up
7 | Bathrooms | Plumbing — both bathrooms | Hassan Plumber | 5500 | 5000 | 2500 | 2500 | 2026-03-01 | 2026-03-20 | 5000 | 0 | 5/5 | Done
8 | Living Room | Feature wall — cladding and lighting | Interior Design | 12000 | 10500 | 5250 | 5250 | 2026-04-01 | 2026-04-15 | 0 | 0 | N/A | In Progress | 50% complete — on schedule
9 | Living Room | Flooring — engineered wood throughout | Floor Masters | 18000 | 16500 | 8250 | 8250 | 2026-04-01 | 2026-04-10 | 16500 | 0 | 5/5 | Done | Beautiful — very happy
10 | Living Room | Painting — all rooms | Raj Painter | 8500 | 7500 | 3750 | 3750 | 2026-04-05 | 2026-04-20 | 0 | 0 | N/A | Planned | After cladding complete
11 | Bedrooms | Built-in wardrobes — 3 bedrooms | Gulf Carpentry | 22000 | 20000 | 10000 | 10000 | 2026-05-01 | 2026-05-25 | 0 | 0 | N/A | Planned | Bespoke fitted — 3 rooms
12 | Bedrooms | False ceiling with LED lighting | Gulf Carpentry | 9500 | 8500 | 4250 | 4250 | 2026-05-01 | 2026-05-15 | 0 | 0 | N/A | Planned | Recessed LED throughout
13 | Exterior | External paint — full villa | Raj Painter | 6500 | 6000 | 3000 | 3000 | 2026-06-01 | 2026-06-15 | 0 | 0 | N/A | Planned | Two-coat weather shield
14 | Exterior | Gate and driveway — iron gate + paving | Gulf Steel | 15000 | 13500 | 6750 | 6750 | 2026-06-01 | 2026-06-30 | 0 | 0 | N/A | Planned
15 | Garden | Landscaping — lawn, plants, irrigation | Green Thumb | 12000 | 11000 | 5500 | 5500 | 2026-06-01 | 2026-06-30 | 0 | 0 | N/A | Planned | Full garden redesign
16 | Electrical | Main DB upgrade — smart switches | Ali Electrician | 8500 | 8000 | 4000 | 4000 | 2026-02-01 | 2026-02-15 | 8000 | 0 | 5/5 | Done | Smart home ready
17 | AC | New AC units x5 — inverter type | AC Masters | 22000 | 20000 | 10000 | 10000 | 2026-02-01 | 2026-02-20 | 19800 | 200 | 5/5 | Done | Energy saving — under budget
18 | Design Fee | Interior designer — full project oversight | Design Studio | 15000 | 12000 | 6000 | 6000 | 2026-01-01 | 2026-12-31 | 12000 | 0 | 5/5 | Active | Full project management
19 | Contingency | 10% contingency reserve | Reserve | 18130 | 18130 | 0 | 18130 |  |  | 0 | 0 | N/A | Reserved | Do not use unless needed
20 | TOTAL | Full renovation — all works | All contractors | 234430 | 212330 | 106580 | 105750 | 2026-02-01 | 2026-07-31 | 95300 | 5280 | N/A | In Progress | 55% spent — on track

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit