## Sprint and Agile Tracker
Sprint and Agile Tracker
Plan and track sprints with user stories, velocity and burndown
Story ID | User Story | Priority | Points | Sprint | Assigned To | Status | % Done | Start | End | Acceptance Criteria
US-001 | As a user I can login with email and password | Critical | 5 | Sprint 1 | Dev A | Done | 100% | 2026-02-08 | 2026-02-21 | Login works — session created — error on fail
US-002 | As a user I can reset password via email | High | 3 | Sprint 1 | Dev B | Done | 100% | 2026-02-08 | 2026-02-21 | Reset link sent within 60 seconds
US-003 | As admin I can view all user accounts | High | 5 | Sprint 1 | Dev A | Done | 100% | 2026-02-08 | 2026-02-21 | Table view with search and filter
US-004 | As user I can view dashboard with KPI tiles | High | 8 | Sprint 2 | Dev B | In Progress | 60% | 2026-02-22 | 2026-03-07 | 5 KPI tiles load within 3 seconds
US-005 | As user I can export reports to PDF | Medium | 5 | Sprint 2 | Dev A | In Progress | 40% | 2026-02-22 | 2026-03-07 | PDF generated in under 10 seconds
US-006 | As user I can set notification preferences | Medium | 3 | Sprint 3 | Dev B | Backlog | 0% | 2026-03-08 | 2026-03-21 | Email and push notifications configurable
US-007 | As admin I can generate audit trail reports | High | 8 | Sprint 3 | Dev A | Backlog | 0% | 2026-03-08 | 2026-03-21 | Full activity log with date filters
US-008 | As user I can integrate with third-party CRM | Low | 13 | Sprint 4 | Dev B | Backlog | 0% | 2026-03-22 | 2026-04-04 | Salesforce and Zoho CRM sync
SPRINT 1 SUMMARY | Done — 13 pts | Velocity: 13
SPRINT 2 SUMMARY | In Progress — 13 pts | Velocity TBD

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit