## IT Change Request Form
IT Change Request Form
Raise and track IT change requests through the change control process
CR ID | Change Title | Requestor | Date | Type | Systems Affected | Business Impact | Risk | Approved By | Approval Date | Impl. Date | Status
CR-2601 | Upgrade DB server v12 to v15 | Dev Lead | 2026-05-01 | Standard | Prod DB | Low — no downtime | Low | IT Manager | 2026-05-03 | 2026-05-10 | Approved
CR-2602 | Add new API endpoint for mobile | Dev A | 2026-05-02 | Standard | API Gateway | Medium | Low | IT Manager | 2026-05-04 | 2026-05-15 | Approved
CR-2603 | Emergency patch — CVE-2026-1234 | CISO | 2026-05-03 | Emergency | All servers | Critical — security | Critical | CTO | 2026-05-03 | 2026-05-03 | Completed
CR-2604 | Migrate file storage to S3 | Infra Lead | 2026-05-04 | Major | File Server | High — 4hr window | Medium | Change Board | 2026-05-10 | 2026-05-25 | Under Review
CR-2605 | Renew SSL certificate — expiry 30-May | IT Admin | 2026-05-05 | Standard | Web servers | High if missed | Medium | IT Manager | 2026-05-06 | 2026-05-28 | Approved
CR-2606 | Deploy bulk email export feature | Dev B | 2026-05-06 | Standard | Email module | Low — new feature | Low | IT Manager | — | 2026-05-20 | Pending
CR-2607 | Upgrade DB server v12 to v16 | Dev Lead | 2026-05-07 | Standard | Prod DB | Low — no downtime | Low | IT Manager | 2026-05-03 | 2026-05-10 | Approved
CR-2608 | Add new API endpoint for mobile | Dev A | 2026-05-08 | Standard | API Gateway | Medium | Low | IT Manager | 2026-05-04 | 2026-05-15 | Approved
CR-2609 | Emergency patch — CVE-2026-1235 | CISO | 2026-05-09 | Emergency | All servers | Critical — security | Critical | CTO | 2026-05-03 | 2026-05-03 | Completed
CR-2610 | Migrate file storage to S4 | Infra Lead | 2026-05-10 | Major | File Server | High — 4hr window | Medium | Change Board | 2026-05-10 | 2026-05-25 | Under Review
CR-2611 | Renew SSL certificate — expiry 30-May | IT Admin | 2026-05-11 | Standard | Web servers | High if missed | Medium | IT Manager | 2026-05-06 | 2026-05-28 | Approved
CR-2612 | Deploy bulk email export feature | Dev B | 2026-05-12 | Standard | Email module | Low — new feature | Low | IT Manager | — | 2026-05-20 | Pending
CR-2613 | Upgrade DB server v12 to v17 | Dev Lead | 2026-05-13 | Standard | Prod DB | Low — no downtime | Low | IT Manager | 2026-05-03 | 2026-05-10 | Approved
CR-2614 | Add new API endpoint for mobile | Dev A | 2026-05-14 | Standard | API Gateway | Medium | Low | IT Manager | 2026-05-04 | 2026-05-15 | Approved

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit