## UAT Test Cases Log
UAT Test Cases Log
User Acceptance Testing template with test scenarios and results
Test ID | Module | Scenario | Test Steps | Test Data | Expected Result | Actual Result | Pass/Fail | Tester | Date | Defect ID
TC-001 | Login | Valid user login | 1.Open app 2.Enter email 3.Enter password 4.Click Login | Email: test@co.in Pass: Test@123 | Dashboard loads — user logged in | Dashboard loaded correctly | Pass | QA Lead | 2026-05-01 | —
TC-002 | Login | Invalid password | 1.Enter valid email 2.Enter wrong password 3.Login | Email: test@co.in Pass: Wrong123 | Error: Invalid credentials | Error displayed correctly | Pass | QA Lead | 2026-05-01 | —
TC-003 | Login | Account lockout after 5 attempts | 1.Enter wrong password 5 times | Any email | Account locked — message shown | Locked on 5th attempt | Pass | QA Lead | 2026-05-01 | —
TC-004 | Dashboard | KPI tiles load correctly | 1.Login 2.Go to dashboard 3.Verify 5 tiles | Valid user account | 5 tiles show data within 3 secs | 4 tiles loaded — Revenue tile blank | Fail | QA Lead | 2026-05-02 | BUG-012
TC-005 | Dashboard | Export to PDF | 1.Open dashboard 2.Click Export 3.Select PDF | Valid user | PDF generated in under 10 seconds | PDF generated in 8 secs — correct | Pass | Client | 2026-05-02 | —
TC-006 | Reports | Date range filter | 1.Open reports 2.Set date range 3.Apply | Any user account | Report shows only selected date range | Filter worked correctly | Pass | QA Lead | 2026-05-02 | —
TC-007 | Admin | Add new user | 1.Login as admin 2.Go to Users 3.Add user | New user details | New user created — email sent | User created — email not sent | Fail | QA Lead | 2026-05-03 | BUG-013
TC-008 | Password | Reset via email | 1.Forgot Password 2.Enter email 3.Check inbox | Registered email | Reset link arrives in 60 seconds | Link in 45 secs — new password worked | Pass | QA Lead | 2026-05-03 | —
TC-009 | Login | Valid user login | 1.Open app 2.Enter email 3.Enter password 4.Click Login | Email: test@co.in Pass: Test@124 | Dashboard loads — user logged in | Dashboard loaded correctly | Pass | QA Lead | 2026-05-01 | —
TC-010 | Login | Invalid password | 1.Enter valid email 2.Enter wrong password 3.Login | Email: test@co.in Pass: Wrong124 | Error: Invalid credentials | Error displayed correctly | Pass | QA Lead | 2026-05-01 | —
TC-011 | Login | Account lockout after 5 attempts | 1.Enter wrong password 5 times | Any email | Account locked — message shown | Locked on 5th attempt | Pass | QA Lead | 2026-05-01 | —
TC-012 | Dashboard | KPI tiles load correctly | 1.Login 2.Go to dashboard 3.Verify 5 tiles | Valid user account | 6 tiles show data within 3 secs | 5 tiles loaded — Revenue tile blank | Fail | QA Lead | 2026-05-02 | BUG-013
TC-013 | Dashboard | Export to PDF | 1.Open dashboard 2.Click Export 3.Select PDF | Valid user | PDF generated in under 10 seconds | PDF generated in 8 secs — correct | Pass | Client | 2026-05-02 | —
TC-014 | Reports | Date range filter | 1.Open reports 2.Set date range 3.Apply | Any user account | Report shows only selected date range | Filter worked correctly | Pass | QA Lead | 2026-05-02 | —
TC-015 | Admin | Add new user | 1.Login as admin 2.Go to Users 3.Add user | New user details | New user created — email sent | User created — email not sent | Fail | QA Lead | 2026-05-03 | BUG-014
TC-016 | Password | Reset via email | 1.Forgot Password 2.Enter email 3.Check inbox | Registered email | Reset link arrives in 60 seconds | Link in 45 secs — new password worked | Pass | QA Lead | 2026-05-03 | —
TC-017 | Login | Valid user login | 1.Open app 2.Enter email 3.Enter password 4.Click Login | Email: test@co.in Pass: Test@125 | Dashboard loads — user logged in | Dashboard loaded correctly | Pass | QA Lead | 2026-05-01 | —
TC-018 | Login | Invalid password | 1.Enter valid email 2.Enter wrong password 3.Login | Email: test@co.in Pass: Wrong125 | Error: Invalid credentials | Error displayed correctly | Pass | QA Lead | 2026-05-01 | —
TC-019 | Login | Account lockout after 5 attempts | 1.Enter wrong password 5 times | Any email | Account locked — message shown | Locked on 5th attempt | Pass | QA Lead | 2026-05-01 | —
TC-020 | Dashboard | KPI tiles load correctly | 1.Login 2.Go to dashboard 3.Verify 5 tiles | Valid user account | 7 tiles show data within 3 secs | 6 tiles loaded — Revenue tile blank | Fail | QA Lead | 2026-05-02 | BUG-014

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit