## Deployment Checklist
Project Deployment Checklist
End-to-end deployment checklist covering pre-deployment, go-live, and post-deployment steps
S.No. | Phase | Task / Check Item | Owner | Target Date | Actual Date | Status | Notes
1 | Pre-Deployment | Code freeze and final build confirmed | Dev Lead | 2026-01-20 | 2026-01-20 | Done | Build v2.4.1
2 | Pre-Deployment | All unit and regression tests passed | QA Team | 2026-01-20 | 2026-01-20 | Done | 0 critical bugs open
3 | Pre-Deployment | Deployment plan reviewed and approved | PM | 2026-01-21 | 2026-01-21 | Done
4 | Pre-Deployment | Rollback plan documented and tested | Dev Lead | 2026-01-21 |  | In Progress | Rollback script ready, test pending
5 | Pre-Deployment | Database backup completed | DBA | 2026-01-22 |  | Pending | Scheduled 23 Jan 2026
6 | Deployment | UAT sign-off received from business | BA | 2026-01-23 |  | Pending
7 | Deployment | Production environment configuration updated | DevOps | 2026-01-23 |  | Pending
8 | Deployment | Deployment executed in production | DevOps | 2026-01-24 |  | Pending
9 | Post-Deployment | Smoke testing completed on production | QA Team | 2026-01-24 |  | Pending
10 | Post-Deployment | Monitoring alerts configured and active | DevOps | 2026-01-24 |  | Pending
11 | Post-Deployment | User communication / release note sent | PM | 2026-01-25 |  | Pending
12 | Post-Deployment | Hypercare support window active (48 hrs) | Support Team | 2026-01-25 |  | Pending
13 | Pre-Deployment | Code freeze and final build confirmed | Dev Lead | 2026-01-20 | 2026-01-20 | Done | Build v2.4.2
14 | Pre-Deployment | All unit and regression tests passed | QA Team | 2026-01-20 | 2026-01-20 | Done | 1 critical bugs open
15 | Pre-Deployment | Deployment plan reviewed and approved | PM | 2026-01-21 | 2026-01-21 | Done
16 | Pre-Deployment | Rollback plan documented and tested | Dev Lead | 2026-01-21 |  | In Progress | Rollback script ready, test pending
17 | Pre-Deployment | Database backup completed | DBA | 2026-01-22 |  | Pending | Scheduled 23 Jan 2027
18 | Deployment | UAT sign-off received from business | BA | 2026-01-23 |  | Pending
19 | Deployment | Production environment configuration updated | DevOps | 2026-01-23 |  | Pending
20 | Deployment | Deployment executed in production | DevOps | 2026-01-24 |  | Pending

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit