## Change Request Log
IT Change Request Log
Track all IT change requests — type, priority, approvals, implementation dates, rollback plans, and post-implementation reviews
S.No. | CR Number | Request Date | Requested By | Department | Change Title | Change Type | Priority | Approved By | Approval Date | Impl. Date | Rollback Plan | Status | Post-Impl. Review | Remarks
1 | CR-2026-001 | 2026-01-02 | Hassan Ali | IT | SAP ERP Patch v12.4 Upgrade | Standard | High | CTO | 2026-01-05 | 2026-01-10 | Yes | Completed | Passed | No issues post upgrade
2 | CR-2026-002 | 2026-01-03 | Ravi Shankar | IT | Firewall Rule Update — Block Port 8080 | Standard | Medium | IT Manager | 2026-01-06 | 2026-01-08 | Yes | Completed | Passed
3 | CR-2026-003 | 2026-01-04 | Ahmed Al Rashid | Finance | New Finance Module in ERP | Major | High | CFO + CTO | 2026-01-10 | 2026-01-20 | Yes | In Progress | Pending | UAT in progress
4 | CR-2026-004 | 2026-01-05 | Priya Sharma | Marketing | CRM Integration with Email Tool | Minor | Low | IT Manager | 2026-01-08 | 2026-01-12 | No | Completed | Passed
5 | CR-2026-005 | 2026-01-06 | Hassan Ali | IT | SSL Certificate Renewal — Website | Emergency | High | CTO | 2026-01-06 | 2026-01-06 | Yes | Completed | Passed | Emergency — cert expired
6 | CR-2026-006 | 2026-01-07 | Suresh Mehta | Finance | New Bank Account Feed in Accounting SW | Standard | Medium | CFO | 2026-01-10 | 2026-01-15 | No | Completed | Passed
7 | CR-2026-007 | 2026-01-08 | Ravi Shankar | IT | Cloud Backup Schedule Update | Minor | Low | IT Manager | 2026-01-10 | 2026-01-12 | No | Completed | Passed | Daily backup now at 02:00
8 | CR-2026-008 | 2026-01-09 | Hassan Ali | IT | Network Switch Replacement — Floor 2 | Standard | Medium | CTO | 2026-01-12 | 2026-01-15 | Yes | Completed | Passed | Planned maintenance window
9 | CR-2026-009 | 2026-01-10 | Ahmed Al Rashid | IT | New Staff VPN Access Setup — 5 users | Minor | Low | IT Manager | 2026-01-12 | 2026-01-13 | No | Completed | Passed
10 | CR-2026-010 | 2026-01-11 | Fatima Hassan | HR | HRMS Payroll Module Update Jan | Standard | High | CTO + HR Dir | 2026-01-14 | 2026-01-16 | Yes | Completed | Passed | WPS output verified
11 | CR-2026-011 | 2026-01-12 | Ravi Shankar | IT | Email Server Migration to Cloud | Major | High | CTO + CEO | 2026-01-20 | 2026-01-25 | Yes | Approved | Pending | Scheduled 25 Jan — Sunday
12 | CR-2026-012 | 2026-01-13 | Hassan Ali | IT | Antivirus Update — All Endpoints | Standard | Medium | IT Manager | 2026-01-15 | 2026-01-16 | No | Completed | Passed | 50 devices updated
13 | CR-2026-013 | 2026-01-14 | Sara Al Noor | Sales | CRM Pipeline Stage Rename | Minor | Low | IT Manager | 2026-01-16 | 2026-01-17 | No | Completed | Passed | Sales team requested
14 | CR-2026-014 | 2026-01-15 | Hassan Ali | IT | Privileged Access Review — Admin Accts | Standard | High | CTO | 2026-01-18 | 2026-01-20 | No | Completed | Passed | Quarterly access review
15 | CR-2026-015 | 2026-01-16 | Ravi Shankar | IT | New Server Rack Installation | Major | Medium | CTO | 2026-01-22 | 2026-01-28 | Yes | Approved | Pending | Hardware arrives 25 Jan
16 | CR-2026-016 | 2026-01-17 | Ahmed Al Rashid | Finance | VAT Return Filing System Update | Standard | High | CFO + CTO | 2026-01-20 | 2026-01-22 | Yes | Completed | Passed | FTA compliance update
17 | CR-2026-017 | 2026-01-18 | Hassan Ali | IT | Wi-Fi Access Point — New Floor 3 Office | Standard | Medium | CTO | 2026-01-22 | 2026-01-24 | No | Completed | Passed
18 | CR-2026-018 | 2026-01-19 | Priya Sharma | Marketing | Google Analytics 4 Migration | Minor | Low | IT Manager | 2026-01-22 | 2026-01-23 | No | Completed | Passed | Universal Analytics sunset
19 | CR-2026-019 | 2026-01-20 | Hassan Ali | IT | Disaster Recovery Plan Test | Standard | High | CTO + COO | 2026-01-25 | 2026-01-28 | Yes | Approved | Pending | Annual DR test — BCP team
20 | CR-2026-020 | 2026-01-21 | Ravi Shankar | IT | Software License Audit — All Systems | Standard | Medium | CTO | 2026-01-25 | 2026-01-28 | No | Approved | Pending | Annual compliance audit

## 📌 More Info
📌 Excel Gurukul Online — Browse All 20 Template Categories
500+ free & premium Excel templates · © 2026 Excel Gurukul Online · https://excelgurukulonline.com · info@excelgurukulonline.com · All templates are subject to terms of use.
Label |  | Description | Link / URL
🌐 Visit Main Website |  | Home page — free downloads, new templates, featured picks | https://excelgurukulonline.com/
📂 Browse All Categories |  | All 20 categories — find the right template in seconds | https://excelgurukulonline.com/templates.php
📧 Request a Custom Template |  | Need something specific? We build it for you! | info@excelgurukulonline.com
# | 📁 TEMPLATE CATEGORY DIRECTORY | What's Inside | 🔗 QUICK LINKS — Click any link to explore
1 | 📊 Project Management | Gantt charts, RACI, WBS, risk registers, project trackers | https://excelgurukulonline.com/templates.php?cat=project-management
2 | 📉 Charts, Dashboards & Analytics | Animated charts, KPI dashboards, speedometers, donut charts | https://excelgurukulonline.com/templates.php?cat=charts-dashboards
3 | 💻 Technology & IT | Sprint trackers, UAT, IT asset register, incident logs | https://excelgurukulonline.com/templates.php?cat=technology-it
4 | 🏛️ Corporate Governance | Board minutes, AGM tracker, ROC filings, compliance calendar | https://excelgurukulonline.com/templates.php?cat=corporate-governance
5 | 📈 Sales & Marketing | Sales pipeline, lead tracker, marketing budget, ROI calculator | https://excelgurukulonline.com/templates.php?cat=sales-marketing
6 | 👥 HR & Workforce Management | Leave tracker, pay slip, WPS UAE, appraisal, onboarding | https://excelgurukulonline.com/templates.php?cat=hr-workforce
7 | 💰 Personal Finance & Budgeting | Stock portfolio, mutual funds, net worth, EMI, SIP planner | https://excelgurukulonline.com/templates.php?cat=personal-finance
8 | 💼 Business & Operations | BCG matrix, balanced scorecard, Porter's five forces, SWOT | https://excelgurukulonline.com/templates.php?cat=business-operations
9 | ⚖️ Legal & Compliance | NDA, service agreement, audit tracker, court date tracker | https://excelgurukulonline.com/templates.php?cat=legal-compliance
10 | 🏠 Household & Family Living | Grocery budget, chore chart, utility bills, vacation packing | https://excelgurukulonline.com/templates.php?cat=household-family
11 | 🏢 Real Estate & Property | Property register, rent tracker, lease calendar, ROI calculator | https://excelgurukulonline.com/templates.php?cat=real-estate
12 | 🎓 Education & Learning | Study timetable, assignment tracker, exam planner, grades log | https://excelgurukulonline.com/templates.php?cat=education-learning
13 | 🎨 Art, Media & Creative | Content calendar, social media planner, video tracker | https://excelgurukulonline.com/templates.php?cat=art-media-creative
14 | ⚽ Sports, Health & Fitness | Fitness tracker, workout planner, diet log, BMI calculator | https://excelgurukulonline.com/templates.php?cat=sports-health-fitness
15 | 🏥 Healthcare & Medical | Medicine tracker, patient log, appointment planner, health diary | https://excelgurukulonline.com/templates.php?cat=healthcare-medical
16 | 🏨 Hospitality & Tourism | Booking register, hotel occupancy, tour planner, revenue tracker | https://excelgurukulonline.com/templates.php?cat=hospitality-tourism
17 | 📦 Inventory & Logistics | Stock register, purchase order, delivery tracker, warehouse log | https://excelgurukulonline.com/templates.php?cat=inventory-logistics
18 | 🏗️ Construction & Engineering | Site progress tracker, material cost, BOQ, snag list | https://excelgurukulonline.com/templates.php?cat=construction-engineering
19 | 🎉 Event Planning & Management | Event budget, guest list, vendor tracker, run-of-show | https://excelgurukulonline.com/templates.php?cat=event-planning
20 | 🤝 Non-Profit & Social Organizations | Donor tracker, grant log, volunteer register, impact report | https://excelgurukulonline.com/templates.php?cat=non-profit